## ReadMeFirst
INFO 8440 Team and Individual Project Plan, Time, Effort, Status Reporting Workbook
*** This is a sample, and a template ****
*** Teams submitting a RACI workbook that is not based on this Template will receive, at best, an Adequate rating ***
Created by: | Bill Nixon |  | Version | 5
History Table:
| Date | Version | Comments
| 2017-08-01 | 1 | Created and published
| 2019-10-17 | 2 | Added Actual RACI Columns, and Task Types
| 2018-12-01 | 3 | Added Person Sheets, and Daily Report
| 2021-01-21 | 4 | Created RACI Deliverables, and RACI Tasks sheets
| 2022-12-21 | 5 | Renamed sheets. Added more documentation and guidance.
Sheets
ReadMeFirst | This sheet. Gives an overview of the entire workbook
RACI Deliverables | Required. The latest version of the RACI Deliverables for the team for this project. This sheet is cloned at the first of every class day, and then updated.
RACI Tasks | Optional. The latest version of the RACI Tasks for the team for this project. This sheet is cloned at the first of every class day, and then updated.
Dlvrbls Day 3-1 | Required. The RACI Deliverables sheet as of Week 3 Day 1 at start of class. This should never be changed. Comparing this to the latest sheet will show the RACI changes, and thus team decisions.
By the time that the project is finished, there must be one backup sheet for each of all but the last 2 days (Briefing/Presentation Days) of the Project
Tasks Day 3-1 | Optional. The RACI Tasks sheet as of Week 3 Day 1 at start of class. This should never be changed.
Person1 | The Daily Time log for Person1 of the Team. Always insert new lines at the base of the list, so that the message at the bottom (Row 47 in the sampe) always stays.
** More Daily Log sheets needed - one for each team member! ** These should be kept in separate workbooks during the project, and submitted separately for final submission **
Gantt | Reserved Sheet for a Ecel based Gantt of the RACI Deliverables Sheet.
For the PM Docs version of this workbook, the Gantt will have no data, and thus no date range graphics, but it will have Excel formulas to create the graphics.
Guidance:
1) | Update RACI data only in the RACI sheet!
2) | The Activity Numbers in the Person Sheets are the code number for the Activity from the RACI
3) | All Required Deliverables for the Final Project submission must be provided in the Delvierables sheets. RFI and PM Docs Deliverable are optional.
4) | Every Deliverable Item must have a Responsible and Accountable person. It is allowable to be A,R, but someone else should do a Quality Check on all person's work.
5) | Formatting is left to you to do. This workbook is given to you as a guide. It must look different than this sample when submitted as INFO 8440 work.
6) | Save your work often. Save different versions of this file as backups.
7) | All dates must be formatted as DD-MMM or DD-MMM-YY 11-Jan-17 or 11-Jan
8) | The RACI-Actual Columns should only be filled in when the Actual differs from the Plan.
9) | Vlookup is used to echo the names of the deliverables into the Tasks sheets and the Gantt sheet
10) | Sheets are created to support filtering, not grouped reporting
11) | The Actual IsBuilt Date in RACI Deliverables indicates the date when the original creator has received a Quality OK rating from the team.
Usually, the component is then included in the final report and/or presentation
12) | In the RACI Deliverables and RACI Tasks sheets, from Row 7 and down, THERE MUST BE NO MERGED CELLS!
13) | Projected Effort data in the RACI+ Deliverables is expected in the Phase 3 Project, but optional in Phase 1
14) | The Deliverable Grouping is optional data.
15) | Minutes of Team Meetings are not required in this course. Instead, this RACI must be kept up to date, and backup sheets done every class day.
16) | This RACI+ workbook will be required as a weekly submission for later weeks in each project. Professor will provide details at that time.

## RACI Deliverables
Team Task Planning and Assignment Worksheet
Project Team (Assigned Group): |  |  | Team G | Course Week | Day
Date (Worksheet version): |  |  | 2022-01-28
[5 empty] | MayurKumar Rafaliya ( Project Manager) | Prajwal Nayak | Anusha Asokan Palat | Jigeesha Kocher | Cathleen Mathew Mundat | Chaitanya keesari
Deliverable Group |  | DlvID | Project Final Deliverables (RFIs and PM Docs Deliverables are optional) | Need / Requirement ID | MayurKum Plan | Prajwal Plan | Anusha A Plan | Jigeesha Plan | Cathleen Plan | Chaitanya keesari | Professor's Marking Item ID# | Start Date | Due Date (M/D/Y) | Actual Effort Days | Actual Start Date (M/D/Y) | Actual IsBuilt Date (M/D/Y) | Done On Date (M/D/Y)
GA | Building | A | Letter of Transmittal | 20 | R |  | A |  |  |  |  | 2022-02-25 | 2022-02-26 | 1
GA | Building | B | Cover Page | 20 |  |  | R | A |  |  |  | 2022-02-25 | 2022-02-26 | 1
GA | Building | C | Page Headers, Footers and Numbering | 20 | A | R | [5 empty] | 2022-02-25 | 2022-02-26 | 1
GA | Building | D | TOC | 20 |  |  |  | R | A |  |  | 2022-02-25 | 2022-02-26 | 1
GA | Building | E | Document History | 20 |  |  |  |  | R | A |  | 2022-02-25 | 2022-02-26 | 1
GA | Building | F | Executive Summary | 21 |  |  | R |  |  | A |  | 2022-02-25 | 2022-02-26 | 1
GA | Building | G | Assumptions | 21 | R |  |  | A |  |  |  | 2022-02-25 | 2022-02-26 | 1
GA | Building | H | Conclusions | 21 |  | R |  |  |  | A |  | 2022-02-25 | 2022-02-26 | 1
GA | Building | I | Background and overview of client | 22 | A |  | R |  |  |  |  | 2022-02-25 | 2022-02-26 | 1
GA | Building | J | Requests for Information with NDA (included as an Appendix) | 22 |  |  | A | R |  |  |  | 2022-02-25 | 2022-02-26 | 1
GA | Building | K | Project Scope Document | 24 | A | A |  | R |  |  |  | 2022-02-25 | 2022-03-05 | 8
GA | Building | L | AS-IS Excel Component sheet | 61 | R | A | [5 empty] | 2022-02-28 | 2022-03-06 | 6
GA | Building | M | AS-IS Excel Component Price sheet with max and min value | 62 |  |  | R |  | A |  |  | 2022-02-28 | 2022-03-08 | 8
GA | Building | N | AS-IS Excel Picking sheet | 68 |  |  |  | R |  | A |  | 2022-02-26 | 2022-03-08 | 10
GA | Building | O | AS-IS Excel Assembly Actions,Components,Tests, Failure Rates and Movements sheet | 69 | R |  |  |  | A |  |  | 2022-02-28 | 2022-03-06 | 6
GA | Building | P | AS-IS Excel Assembly Assembly - Labour Costs | 71 |  |  | A |  |  | R |  | 2022-02-27 | 2022-03-09 | 10
GA | Building | Q | AS-IS Excel Assembly - Component Costs,Totals (Running and Grand) | 72 |  | A |  |  | R |  |  | 2022-02-28 | 2022-03-09 | 9
GA | Building | R | AS-IS Excel Assembly - Labour & Component Costs,Totals (Running and Grand) response to Test fails | 73 | A |  | R |  |  |  |  | 2022-02-28 | 2022-03-09 | 9
GA | Building | S | AS-IS Excel Assembly Movement | 74 |  |  | R | A |  |  |  | 2022-02-28 | 2022-03-09 | 9
GA | Building | T | Business Challenges | 22 | R |  | A |  |  |  |  | 2022-02-27 | 2022-03-04 | 5
GA | Building | U | Current Brands Involved and their Statuses | 26 |  |  |  |  | A | R |  | 2022-02-27 | 2022-03-04 | 5
GA | Building | V | AS-IS Excel Employee detail sheet |  |  |  |  | R |  | A |  | 2022-03-07 | 2022-03-09 | 2
GA | Building | W | AS-IS Excel Schedule sheet | 63 |  | R |  |  | A |  |  | 2022-02-28 | 2022-03-06 | 6
GA | Building | X | AS-IS Spaghetti Diagram | 65 |  |  | R | R | A |  |  | 2022-02-28 | 2022-03-06 | 6
GA | Building | Y | AS-IS Spaghetti Diagram labels and Notes | 66 | A | R |  |  | R |  |  | 2022-02-28 | 2022-03-06 | 6
GA | Building | Z | Gantt Chart |  |  | A |  |  | R |  |  | 2022-02-27 | 2022-03-04 | 5
GA | Building | AA | AS-IS Daily production sheet | 75 |  |  |  | A |  | R |  | 2022-02-27 | 2022-03-08 | 9
GA | Building | AB | AS-IS Average Production sheet | 75 |  |  | A |  | R |  |  | 2022-02-27 | 2022-03-08 | 9
GA | Building | AC | AS-IS Wholesale sheet | 76 |  | R |  |  | A |  |  | 2022-02-27 | 2022-03-08 | 9
GA | Building | AD | AS-IS Workbook Documentation | 76 | R | [6 empty] | 2022-02-27 | 2022-03-07 | 8
GA | Building | AE | AS-IS Profit and Loss Model (P&L) data | 77 |  | R |  | A |  |  |  | 2022-02-27 | 2022-03-08 | 9
GA | Building | AF | AS-IS Profit and Loss Model (P&L) calculations | 78 |  | R |  |  | A |  |  | 2022-02-27 | 2022-03-07 | 8
GA | Building | AG | AS-IS Profit and Loss Model (P&L) income calculations | 79 |  | A |  |  |  | R |  | 2022-02-27 | 2022-03-07 | 8
GA | Building | AH | Detailed References for all Sources of Knowledge | 23 |  |  | A | R |  |  |  | 2022-02-27 | 2022-03-07 | 8
GA | Building | AI | Possible Future Analysis and Development for TrackR manufacturing process | 26 |  |  |  | A | R |  |  | 2022-02-26 | 2022-03-05 | 7
GA | Building | AJ | Measuring Success and Failure in improving TrackR manufacturing process | 26 | R | A | [5 empty] | 2022-02-26 | 2022-03-05 | 7
GA | Building | AK | Probable Benefits of Changing TrackR manufacturing Process | 26 |  |  |  | A |  | R |  | 2022-02-25 | 2022-03-05 | 8
GA | Building | AL | Suggestion Overview | 1 |  |  | R |  | A |  |  | 2022-03-09 | 2022-03-13 | 4
GA | Building | AM | Six sigma and Failure reduction process report | 4 | R |  |  |  |  | A |  | 2022-03-09 | 2022-03-13 | 4
GA | Building | AN | TO BE model - Six sigma process | 3 | R | A | [5 empty] | 2022-03-09 | 2022-03-29 | 20
GA | Building | AO | Siplace Impact and ROI report | 5 | R |  | A |  | R |  |  | 2022-03-09 | 2022-03-15 | 6
GA | Building | AP | TO BE model - Siplace machine impact | 5 | A |  | A |  | R |  |  | 2022-03-09 | 2022-03-28 | 19
GA | Building | AQ | TO BE Picking process - Financial excel model | 43 |  | R |  | A |  |  |  | 2022-03-09 | 2022-03-28 | 19
GA | Building | AR | TO BE Assembly process - Financial excel model | 43 |  |  |  | R |  | R |  | 2022-03-09 | 2022-03-28 | 19
GA | Building | AS | TO BE Staffing process - Financial excel model | 43 |  |  | R |  |  | A |  | 2022-03-09 | 2022-03-28 | 19
GA | Building | AT | Training,Needs and plans | 6 |  |  |  |  | A | R |  | 2022-03-22 | 2022-03-31 | 9
GA | Building | AU | Suggestion on Environment Changes | 7 |  | A | R |  |  |  |  | 2022-03-10 | 2022-03-20 | 10
GA | Building | AV | Constraints on Restructuring workspace | 9 | A |  |  |  | R |  |  | 2022-03-20 | 2022-03-31 | 11
GF | Closing | BX | Merged Final Report |  | R |  | R |  |  |  |  | 2022-03-25 | 2022-03-31 | 6
GF | Closing | BY | Powerpoint Presentation |  |  |  |  | A | R |  |  | 2022-03-27 | 2022-03-31 | 4
GF | Closing | BZ | Final RFI report | 23 | R |  | A |  |  |  |  | 2022-03-25 | 2022-03-31 | 6
GF | Closing | CA | RACI+, Documentation, Backup Sheets |  |  | R |  |  | A |  |  | 2022-02-25 | 2022-04-01 | 35
GF | Closing | CB | Time and Effort Reporting | 25 | R | R | R | R | R | R |  | 2022-02-25 | 2022-04-01 | 35
[5 empty] | MayurKum | Prajwal | Anusha A | Jigeesha | Cathleen | Chaitany
|  |  |  | R | 13 | 10 | 12 | 9 | 11 | 8
|  |  |  | A | 7 | 8 | 9 | 9 | 11 | 7
|  |  |  | C | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | MayurKum | Prajwal | Anusha A | Jigeesha | Cathleen | Chaitany

## RACI Tasks
Team Task Planning and Assignment Worksheet
Project Team (Assigned Group): |  |  | Team G | Course Week | Day
Date (Worksheet version): |  |  | 2020-09-17 | 3 | 2
[5 empty] | MayurKumar Rafaliya ( Project Manager) | Prajwal Nayak (RACI Keeper) | Anusha Ashokan Palat | Jigeesha Kocher | Cathleen Mathew Mundat | Chaitanya Keesari | [9 empty] | MayurKumar Rafaliya ( Project Manager) | Prajwal Nayak (RACI Keeper) | Anusha Ashokan Palat | Jigeesha Kocher | Cathleen Mathew Mundat | Chaitanya Keesari
DlvID | TaskID | Project Final Deliverables (No Verb Words at the start) | Activity / Task (VERB: Subject) | Project Phase (see WBS) | MayurKumar | Prajwal | Anusha A | Jigeesha | Cathleen | Chaitany | Start Date | Due Date (M/D/Y) | Actual Effort (Days) | Projected Effort (person - hrs) | Task Type - Team, Single or SubTeam | Task Version | Actual Start Date (M/D/Y) | Done On Date (M/D/Y) | RACI - ACTUAL
A | 1.1 | Letter of Transmittal | Develop a cover page | Create | R |  | A |  |  |  | 2022-02-25 | 2022-02-26 | 1 | 0
A | 1.2 | Letter of Transmittal | Develop a cover page | Pack and publish | R |  | A |  |  |  | 2022-02-25 | 2022-02-26 | 1 | 0
B | 2.1 | Cover Page | Develop a cover letter | Create |  |  | R | A |  |  | 2022-02-25 | 2022-02-26 | 1 | 0 |  |  |  |  | R | C | C
B | 2.2 | Cover Page | Develop a cover letter | Pack and publish |  |  | R | A |  |  | 2022-02-25 | 2022-02-26 | 1 | 0
C | 3.1 | Page Headers, Footers and Numbering | Develop a header, footer and numbering | Create | A | R |  |  |  |  | 2022-02-25 | 2022-02-26 | 1 | 0
C | 3.2 | Page Headers, Footers and Numbering | Develop header, footer and numbering | Pack and publish | A | R |  |  |  |  | 2022-02-25 | 2022-02-26 | 1 | 0
D | 4.1 | TOC | Create a table of content | Publish |  |  |  | R | A |  | 2022-02-25 | 2022-02-26 | 1 | 0
E | 5.1 | Document History | Research about documnent history document | Research |  |  |  |  | R | A | 2022-02-25 | 2022-02-26 | 1 | 0
E | 5.2 | Document History | Develop document history document | Create |  |  |  |  | R | A | 2022-02-25 | 2022-02-26 | 1 | 0
E | 5.3 | Document History | Publish document history document | Publish |  |  |  |  | R | A | 2022-02-25 | 2022-02-26 | 1 | 0
F | 6.1 | Executive Summary | Write summary for executives | Create |  |  | R |  |  | A | 2022-02-25 | 2022-02-26 | 1 | 0
F | 6.2 | Executive Summary | publish summary for executive summary | Publish |  |  | R |  |  | A | 2022-02-25 | 2022-02-26 | 1 | 0
G | 7.1 | Assumptions | Gather assumptions | Research | R |  |  | A |  |  | 2022-02-25 | 2022-02-26 | 1 | 0
G | 7.2 | Assumptions | Create asuumptions | Create | R |  |  | A |  |  | 2022-02-25 | 2022-02-26 | 1 | 0
G | 7.3 | Assumptions | Publish assumptions | Pack and publish | R |  |  | A |  |  | 2022-02-25 | 2022-02-26 | 1 | 0
H | 8.1 | Conclusions | Create conclusion | Create |  | R |  |  |  | A | 2022-02-25 | 2022-02-26 | 1 | 0
H | 8.2 | Conclusions | Publish conclusion | Publish |  | R |  |  |  | A | 2022-02-25 | 2022-02-26 | 1 | 0
I | 9.1 | Background and overview of client | Develop document | Create | A |  | R |  |  |  | 2022-02-25 | 2022-02-26 | 1 | 0
I | 9.2 | Background and overview of client | Publish final document | Publish | A |  | R |  |  |  | 2022-02-25 | 2022-02-26 | 1 | 0
J | 10.1 | Requests for Information with NDA (included as an Appendix) | Create RFI Document | Create |  |  | A | R |  |  | 2022-02-25 | 2022-02-26 | 1 | 0
J | 10.2 | Requests for Information with NDA (included as an Appendix) | Look out for questions need to ask | Research |  |  | A | R |  |  | 2022-02-25 | 2022-02-26 | 1 | 0
J | 10.3 | Requests for Information with NDA (included as an Appendix) | Prepare Final RFI Document | Pack and publish |  |  | A | R |  |  | 2022-02-25 | 2022-02-26 | 1 | 0
K | 11.1 | Project Scope Document | Creating Document | Create | A | A |  | R |  |  | 2022-02-25 | 2022-03-05 | 8 | 0
K | 11.2 | Project Scope Document | Develop content for scope | Research | A | A |  | R |  |  | 2022-02-25 | 2022-03-05 | 8 | 0
K | 11.3 | Project Scope Document | Finalize and publish | Pack and publish | A | A |  | R |  |  | 2022-02-25 | 2022-03-05 | 8 | 0
L | 12.1 | AS-IS Excel Component sheet | Creating component sheet | Create | R | A |  |  |  |  | 2022-02-28 | 2022-03-06 | 6 | 0
L | 12.2 | AS-IS Excel Component sheet | Research about component | Research | R | A |  |  |  |  | 2022-02-28 | 2022-03-06 | 6 | 0
L | 12.3 | AS-IS Excel Component sheet | Publish and finalize | Pack and publish | R | A |  |  |  |  | 2022-02-28 | 2022-03-06 | 6 | 0
M | 13.1 | AS-IS Excel Component Price sheet with max and min value | map sheet with pos | Create |  |  | R |  | A |  | 2022-02-28 | 2022-03-08 | 8 | 0
M | 13.2 | AS-IS Excel Component Price sheet with max and min value | Prepare Decision flow | Research |  |  | R |  | A |  | 2022-02-28 | 2022-03-08 | 8 | 0
M | 13.3 | AS-IS Excel Component Price sheet with max and min value | Publish and finalize | Package and publish |  |  | R |  | A |  | 2022-02-28 | 2022-03-08 | 8 | 0
N | 14.1 | AS-IS Excel Picking sheet | Prepare picking times and speed | Create |  |  |  | R |  | A | 2022-02-26 | 2022-03-08 | 10 | 0
N | 14.2 | AS-IS Excel Picking sheet | develop and research | Research |  |  |  | R |  | A | 2022-02-26 | 2022-03-08 | 10 | 0
N | 14.3 | AS-IS Excel Picking sheet | Publish and finalize | Package and publish |  |  |  | R |  | A | 2022-02-26 | 2022-03-08 | 10 | 0
O | 15.1 | AS-IS Excel Assembly Actions,Components,Tests, Failure Rates and Movements sheet | Develop list | Create | R |  |  |  | A |  | 2022-02-28 | 2022-03-06 | 6 | 0
O | 15.2 | AS-IS Excel Assembly Actions,Components,Tests, Failure Rates and Movements sheet | Publish | Package and publish | R |  |  |  | A |  | 2022-02-28 | 2022-03-06 | 6 | 0
p | 16.1 | AS-IS Excel Assembly Assembly - Labour Costs | Develop Document | Create |  |  | A |  |  | R | 2022-02-27 | 2022-03-09 | 10 | 0
p | 16.2 | AS-IS Excel Assembly Assembly - Labour Costs | Analyse and collect information | Research |  |  | A |  |  | R | 2022-02-27 | 2022-03-09 | 10 | 0
P | 16.3 | AS-IS Excel Assembly Assembly - Labour Costs | Finalize and publish | Package and publish |  |  | A |  |  | R | 2022-02-27 | 2022-03-09 | 10 | 0
Q | 17.1 | AS-IS Excel Assembly - Component Costs,Totals (Running and Grand) | Develop Document | Create |  | A |  |  | R |  | 2022-02-28 | 2022-03-09 | 9 | 0
Q | 17.2 | AS-IS Excel Assembly - Component Costs,Totals (Running and Grand) | Analyse and collect information | Research |  | A |  |  | R |  | 2022-02-28 | 2022-03-09 | 9 | 0
Q | 17.3 | AS-IS Excel Assembly - Component Costs,Totals (Running and Grand) | Finalize and publish | Package and publish |  | A |  |  | R |  | 2022-02-28 | 2022-03-09 | 9 | 0
R | 18.1 | AS-IS Excel Assembly - Labour & Component Costs,Totals (Running and Grand) response to Test fails | Develop Document | Create | A |  | R |  |  |  | 2022-02-28 | 2022-03-09 | 9 | 0
R | 18.2 | AS-IS Excel Assembly - Labour & Component Costs,Totals (Running and Grand) response to Test fails | Analyse and collect information | Research | A |  | R |  |  |  | 2022-02-28 | 2022-03-09 | 9 | 0
R | 18.3 | AS-IS Excel Assembly - Labour & Component Costs,Totals (Running and Grand) response to Test fails | Finalize and publish | Package and publish | A |  | R |  |  |  | 2022-02-28 | 2022-03-09 | 9 | 0
S | 19.1 | AS-IS Excel Assembly Movement | Develop Document | Create |  |  | R | A |  |  | 2022-02-28 | 2022-03-09 | 9 | 0
S | 19.2 | AS-IS Excel Assembly Movement | Finalize and publish | Package and publish |  |  | R | A |  |  | 2022-02-28 | 2022-03-09 | 9 | 0
T | 20.1 | Business Challenges | Develop Document | Create | R |  | A |  |  |  | 2022-02-27 | 2022-03-04 | 5 | 0
T | 20.2 | Business Challenges | Analyse and collect information | Research | R |  | A |  |  |  | 2022-02-27 | 2022-03-04 | 5 | 0
T | 20.3 | Business Challenges | Finalize and publish | Package and publish | R |  | A |  |  |  | 2022-02-27 | 2022-03-04 | 5 | 0
U | 21.1 | Current Brands Involved and their Statuses | Develop Document | Create |  |  |  |  | A | R | 2022-02-27 | 2022-03-04 | 5 | 0
U | 21.2 | Current Brands Involved and their Statuses | Analyse and collect information | Research |  |  |  |  | A | R | 2022-02-27 | 2022-03-04 | 5 | 0
U | 21.3 | Current Brands Involved and their Statuses | Finalize and publish | Package and publish |  |  |  |  | A | R | 2022-02-27 | 2022-03-04 | 5 | 0
V | 22.1 | AS-IS Excel Employee detail sheet | Develop Document | Create |  |  |  | R |  | A | 2022-03-07 | 2022-03-09 | 2 | 0
V | 22.2 | AS-IS Excel Employee detail sheet | Analyse and list out employee | Research |  |  |  | R |  | A | 2022-03-07 | 2022-03-09 | 2 | 0
V | 22.3 | AS-IS Excel Employee detail sheet | Finalize and publish | Package and publish |  |  |  | R |  | A | 2022-03-07 | 2022-03-09 | 2 | 0
W | 23.1 | AS-IS Excel Schedule sheet | Develop Document | Create |  | R |  |  | A |  | 2022-02-28 | 2022-03-06 | 6 | 0
w | 23.2 | AS-IS Excel Schedule sheet | Finalize and publish | Package and publish |  | R |  |  | A |  | 2022-02-28 | 2022-03-06 | 6 | 0
X | 24.1 | AS-IS Spaghetti Diagram | Develop Document | Create |  |  | R | R | A |  | 2022-02-28 | 2022-03-06 | 6 | 0
X | 24.2 | AS-IS Spaghetti Diagram | Analyse and document | Research |  |  | R | R | A |  | 2022-02-28 | 2022-03-06 | 6 | 0
X | 24.3 | AS-IS Spaghetti Diagram | Finalize and publish | Package and publish |  |  | R | R | A |  | 2022-02-28 | 2022-03-06 | 6 | 0
Y | 25.1 | AS-IS Spaghetti Diagram labels and Notes | Develop Document | Create | A | R |  |  | R |  | 2022-02-28 | 2022-03-06 | 6 | 0
Y | 25.2 | AS-IS Spaghetti Diagram labels and Notes | Analyse and plan | Research | A | R |  |  | R |  | 2022-02-28 | 2022-03-06 | 6 | 0
Y | 25.3 | AS-IS Spaghetti Diagram labels and Notes | Finalize and publish | Package and publish | A | R |  |  | R |  | 2022-02-28 | 2022-03-06 | 6 | 0
Z | 26.1 | Gantt Chart | Develop Document | Create |  | A |  |  | R |  | 2022-02-27 | 2022-03-04 | 5 | 0
Z | 26.2 | Gantt Chart | Finalize and publish | Package and publish |  | A |  |  | R |  | 2022-02-27 | 2022-03-04 | 5 | 0
AA | 27.1 | AS-IS Daily production sheet | Develop production sheet | Create |  |  |  | A |  | R | 2022-02-27 | 2022-03-08 | 9 | 0
AA | 27.2 | AS-IS Daily production sheet | Collect and analyze data from Trackr | Research |  |  |  | A |  | R | 2022-02-27 | 2022-03-08 | 9 | 0
AA | 27.3 | AS-IS Daily production sheet | Finalize and publish | Package and publish |  |  |  | A |  | R | 2022-02-27 | 2022-03-08 | 9 | 0
AB | 28.1 | AS-IS Average Production sheet | Develop production sheet | Create |  |  | A |  | R |  | 2022-02-27 | 2022-03-08 | 9 | 0
AB | 28.2 | AS-IS Average Production sheet | Collect and analyze data from daily production sheet | Research |  |  | A |  | R |  | 2022-02-27 | 2022-03-08 | 9 | 0
AB | 28.3 | AS-IS Average Production sheet | Finalize and publish | Package and publish |  |  | A |  | R |  | 2022-02-27 | 2022-03-08 | 9 | 0
AC | 29.1 | AS-IS Wholesale sheet | Develop wholesale sheet | Create |  | R |  |  | A |  | 2022-02-27 | 2022-03-08 | 9 | 0
AC | 29.2 | AS-IS Wholesale sheet | Collect and analyze data from Trackr | Research |  | R |  |  | A |  | 2022-02-27 | 2022-03-08 | 9 | 0
AC | 29.3 | AS-IS Wholesale sheet | Finalize and publish | Package and publish |  | R |  |  | A |  | 2022-02-27 | 2022-03-08 | 9 | 0
AD | 30.1 | AS-IS Workbook Documentation | Create source list | Create | R | [5 empty] | 2022-02-27 | 2022-03-07 | 8 | 0
AD | 30.2 | AS-IS Workbook Documentation | analyze and collect information | Research | R | [5 empty] | 2022-02-27 | 2022-03-07 | 8 | 0
AD | 30.3 | AS-IS Workbook Documentation | Publish | Package and publish | R | [5 empty] | 2022-02-27 | 2022-03-07 | 8 | 0
AE | 31.1 | AS-IS Profit and Loss Model (P&L) data | Create source list | Create |  | R |  | A |  |  | 2022-02-27 | 2022-03-08 | 9 | 0
AE | 31.2 | AS-IS Profit and Loss Model (P&L) data | Publish | Package and publish |  | R |  | A |  |  | 2022-02-27 | 2022-03-08 | 9 | 0
AF | 32.1 | AS-IS Profit and Loss Model (P&L) calculations | Create document for calculations | Create |  | R |  |  | A |  | 2022-02-27 | 2022-03-07 | 8 | 0
AF | 32.2 | AS-IS Profit and Loss Model (P&L) calculations | Prepare and Finalize | Package and publish |  | R |  |  | A |  | 2022-02-27 | 2022-03-07 | 8 | 0
AG | 33.1 | AS-IS Profit and Loss Model (P&L) income calculations | Create document for calculations | Create |  | A |  |  |  | R | 2022-02-27 | 2022-03-07 | 8 | 0
AG | 33.2 | AS-IS Profit and Loss Model (P&L) income calculations | Prepare and Finalize | Package and publish |  | A |  |  |  | R | 2022-02-27 | 2022-03-07 | 8 | 0
AH | 34.1 | Detailed References for all Sources of Knowledge | Create references for all sources | Create |  |  | A | R |  |  | 2022-02-27 | 2022-03-07 | 8 | 0
AH | 34.2 | Detailed References for all Sources of Knowledge | Prepare and Finalize | Package and publish |  |  | A | R |  |  | 2022-02-27 | 2022-03-07 | 8 | 0
AI | 35.1 | Possible Future Analysis and Development for TrackR manufacturing process | Create analysis document | Create |  |  |  | A | R |  | 2022-02-26 | 2022-03-05 | 7 | 0
AI | 35.2 | Possible Future Analysis and Development for TrackR manufacturing process | Finalize and publish | Package and publish |  |  |  | A | R |  | 2022-02-26 | 2022-03-05 | 7 | 0
AJ | 36.1 | Measuring Success and Failure in improving TrackR manufacturing process | Develop document | Create | R | A |  |  |  |  | 2022-02-26 | 2022-03-05 | 7 | 0
AJ | 36.2 | Measuring Success and Failure in improving TrackR manufacturing process | Analyze and prepare sucess and failure | Research | R | A |  |  |  |  | 2022-02-26 | 2022-03-05 | 7 | 0
AJ | 36.3 | Measuring Success and Failure in improving TrackR manufacturing process | Finalize and publish | Package and publish | R | A |  |  |  |  | 2022-02-26 | 2022-03-05 | 7 | 0
AK | 37.1 | Probable Benefits of Changing TrackR manufacturing Process | Develop benefits | Create |  |  |  | A |  | R | 2022-02-25 | 2022-03-05 | 8 | 0
AK | 37.2 | Probable Benefits of Changing TrackR manufacturing Process | Analyze and collect information | Research |  |  |  | A |  | R | 2022-02-25 | 2022-03-05 | 8 | 0
AK | 37.3 | Probable Benefits of Changing TrackR manufacturing Process | Finalize and publish | Package and publish |  |  |  | A |  | R | 2022-02-25 | 2022-03-05 | 8 | 0
AL | 38.1 | Suggestion Overview | Create suggestion overview | Create |  |  | R |  | A |  | 2022-03-09 | 2022-03-13 | 4 | 0
AL | 38.2 | Suggestion Overview | Analyze and collect information | Research |  |  | R |  | A |  | 2022-03-09 | 2022-03-13 | 4 | 0
AL | 38.3 | Suggestion Overview | Finalize and publish | Package and publish |  |  | R |  | A |  | 2022-03-09 | 2022-03-13 | 4 | 0
AM | 39.1 | Six sigma and Failure reduction process report | Create six sigma process | Create | R |  |  |  |  | A | 2022-03-09 | 2022-03-13 | 4 | 0
AM | 39.2 | Six sigma and Failure reduction process report | Analyze and collect information | Research | R |  |  |  |  | A | 2022-03-09 | 2022-03-13 | 4 | 0
AM | 39.3 | Six sigma and Failure reduction process report | Finalize and publish | Package and publish | R |  |  |  |  | A | 2022-03-09 | 2022-03-13 | 4 | 0
AN | 40.1 | TO BE model - Six sigma process | Create general to be model - six sigma process | Create | R | A |  |  |  |  | 2022-03-09 | 2022-03-29 | 20 | 0
AN | 40.2 | TO BE model - Six sigma process | Collect all information | Research | R | A |  |  |  |  | 2022-03-09 | 2022-03-29 | 20 | 0
AN | 40.3 | TO BE model - Six sigma process | Finalize and publish | Package and publish | R | A |  |  |  |  | 2022-03-09 | 2022-03-29 | 20 | 0
AO | 41.1 | Siplace Impact and ROI report | Develop document for Siplace machine | Create | R |  | A |  | R |  | 2022-03-09 | 2022-03-15 | 6 | 0
AO | 41.2 | Siplace Impact and ROI report | Analyze and identify impact | Research | R |  | A |  | R |  | 2022-03-09 | 2022-03-15 | 6 | 0
AO | 41.3 | Siplace Impact and ROI report | Prepare and Finalize | Package and publish | R |  | A |  | R |  | 2022-03-09 | 2022-03-15 | 6 | 0
AP | 42.1 | TO BE model - Siplace machine impact | Develop document for to be process | Create | A |  | A |  | R |  | 2022-03-09 | 2022-03-28 | 19 | 0
AP | 42.2 | TO BE model - Siplace machine impact | Analyze and identify metric | Research | A |  | A |  | R |  | 2022-03-09 | 2022-03-28 | 19 | 0
AP | 42.3 | TO BE model - Siplace machine impact | Prepare and Finalize | Package and publish | A |  | A |  | R |  | 2022-03-09 | 2022-03-28 | 19 | 0
AQ | 43.1 | TO BE Picking process - Financial excel model | Develop document for To BE picking process | Create |  | R |  | A |  |  | 2022-03-09 | 2022-03-28 | 19 | 0
AQ | 43.2 | TO BE Picking process - Financial excel model | Analyze and identify metric | Research |  | R |  | A |  |  | 2022-03-09 | 2022-03-28 | 19 | 0
AQ | 43.3 | TO BE Picking process - Financial excel model | Prepare and Finalize | Package and publish |  | R |  | A |  |  | 2022-03-09 | 2022-03-28 | 19 | 0
AR | 44.1 | TO BE Assembly process - Financial excel model | Develop document for TO BE assembly process | Create |  |  |  | R |  | R | 2022-03-09 | 2022-03-28 | 19 | 0 |  |  |  |  | R | R | R | R | R
AR | 44.2 | TO BE Assembly process - Financial excel model | Analyze and identify metric | Research |  |  |  | R |  | R | 2022-03-09 | 2022-03-28 | 19 | 0
AR | 44.3 | TO BE Assembly process - Financial excel model | Prepare and Finalize | Package and publish |  |  |  | R |  | R | 2022-03-09 | 2022-03-28 | 19 | 0
AS | 45.1 | TO BE Staffing process - Financial excel model | Develop document for TO BE Staffing process | Create |  |  | R |  |  | A | 2022-03-09 | 2022-03-28 | 19 | 0 |  |  |  |  | R | R | Absent | R | R
As | 45.2 | TO BE Staffing process - Financial excel model | Analyze and identify process | Research |  |  | R |  |  | A | 2022-03-09 | 2022-03-28 | 19 | 0
AS | 45.3 | TO BE Staffing process - Financial excel model | Prepare and Finalize | Package and publish |  |  | R |  |  | A | 2022-03-09 | 2022-03-28 | 19 | 0
AT | 46.1 | Training,Needs and plans | Develop document for Training | Create |  |  |  |  | A | R | 2022-03-22 | 2022-03-31 | 9 | 0
AT | 46.2 | Training,Needs and plans | Analyze and identify needa and plans | Research |  |  |  |  | A | R | 2022-03-22 | 2022-03-31 | 9 | 0
AT | 46.3 | Training,Needs and plans | Prepare and Finalize | Package and publish |  |  |  |  | A | R | 2022-03-22 | 2022-03-31 | 9 | 0
AU | 47.1 | Suggestion on Environment Changes | Develop document | Create |  | A | R |  |  |  | 2022-03-10 | 2022-03-20 | 10 | 0
AU | 47.2 | Suggestion on Environment Changes | Finalize document | Publish |  | A | R |  |  |  | 2022-03-10 | 2022-03-20 | 10 | 0
AV | 48.1 | Constraints on Restructuring workspace | Develop document for business success | Create | A |  |  |  | R |  | 2022-03-20 | 2022-03-31 | 11 | 0
AV | 48.2 | Constraints on Restructuring workspace | Analyse and collect information | Research | A |  |  |  | R |  | 2022-03-20 | 2022-03-31 | 11 | 0
AV | 48.3 | Constraints on Restructuring workspace | Finalize and Publish | Package and Publish | A |  |  |  | R |  | 2022-03-20 | 2022-03-31 | 11 | 0
BX | 76.1 | Merged Final Report | Gather all the inforamtion for Final Report | Research | R |  | R |  |  |  | 2022-03-25 | 2022-03-31 | 6 | 0
BX | 76.2 | Merged Final Report | Create Final merged Final report | Create | R |  | R |  |  |  | 2022-03-25 | 2022-03-31 | 6 | 0
BX | 76.3 | Merged Final Report | Edit and update all the Final Merged document | Review | R |  | R |  |  |  | 2022-03-25 | 2022-03-31 | 6 | 0
BX | 76.4 | Merged Final Report | Pack and Publish Final Report | Pack and Publish | R |  | R |  |  |  | 2022-03-25 | 2022-03-31 | 6 | 0
BY | 77.1 | Powerpoint Presentation | Gather all the information for Power Persentation | Research |  |  |  | A | R |  | 2022-03-27 | 2022-03-31 | 4 | 0
BY | 77.2 | Powerpoint Presentation | Create a Power Point Presentation | Create |  |  |  | A | R |  | 2022-03-27 | 2022-03-31 | 4 | 0
BY | 77.3 | Powerpoint Presentation | Pack and Publish all the information | Pack and Publish |  |  |  | A | R |  | 2022-03-27 | 2022-03-31 | 4 | 0
BZ | 78.1 | Final RFI report | Gather all the information for RFI Report | Research | R |  | A |  |  |  | 2022-03-25 | 2022-03-31 | 6 | 0
BZ | 78.2 | Final RFI report | Merge all the information for RFI Report | Create | R |  | A |  |  |  | 2022-03-25 | 2022-03-31 | 6 | 0
BZ | 78.3 | Final RFI report | Publish the RFI Report | Pack and Publish | R |  | A |  |  |  | 2022-03-25 | 2022-03-31 | 6 | 0
CA | 79.1 | RACI+, Documentation, Backup Sheets | Create a RACI+, Documentation and Backup Sheets | Research |  | R |  |  | A |  | 2022-02-25 | 2022-04-01 | 35 | 0
CA | 79.2 | RACI+, Documentation, Backup Sheets | Create a RACI+, Documentation and Backup Sheets | Create |  | R |  |  | A |  | 2022-02-25 | 2022-04-01 | 35 | 0
CA | 79.3 | RACI+, Documentation, Backup Sheets | Create a RACI+, Documentation and Backup Sheets | Pack and Publish |  | R |  |  | A |  | 2022-02-25 | 2022-04-01 | 35 | 0
CB | 80.1 | Time and Effort Reporting | Create a Time and Reporting sheet | Research | R | R | R | R | R | R | 2022-02-25 | 2022-04-01 | 35 | 0
CB | 80.2 | Time and Effort Reporting | Create a Time and Reporting sheet | Create | R | R | R | R | R | R | 2022-02-25 | 2022-04-01 | 35 | 0
CB | 80.3 | Time and Effort Reporting | Create a Time and Reporting sheet | Pack and Publish | R | R | R | R | R | R | 2022-02-25 | 2022-04-01 | 35 | 0
[8 empty] | MayurKum | Prajwal | Anusha A | Jigeesha | Cathleen | Chaitany
[6 empty] | Analysis of Plan R, A, C, I's: | R | 38 | 25 | 32 | 24 | 31 | 23
[7 empty] | A | 19 | 21 | 25 | 23 | 28 | 19
[7 empty] | C | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | I | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | MayurKum | Prajwal | Anusha A | Jigeesha | Cathleen | Chaitany

## Gantt sheet
TaskID | Task | Start date | End Date | Duration
J | Requests for Information with NDA (included as an Appendix) | 2022-02-25 | 2022-02-26 | 1
A | Letter of Transmittal | 2022-02-25 | 2022-02-26 | 1
B | Cover Page | 2022-02-25 | 2022-02-26 | 1
C | Page Headers, Footers and Numbering | 2022-02-25 | 2022-02-26 | 1
D | TOC | 2022-02-25 | 2022-02-26 | 1
E | Document History | 2022-02-25 | 2022-02-26 | 1
F | Executive Summary | 2022-02-25 | 2022-02-26 | 1
G | Assumptions | 2022-02-25 | 2022-02-26 | 1
H | Conclusions | 2022-02-25 | 2022-02-26 | 1
I | Background and overview of client | 2022-02-25 | 2022-02-26 | 1
T | Business Challenges | 2022-02-27 | 2022-03-04 | 5
U | Current Brands Involved and their Statuses | 2022-02-27 | 2022-03-04 | 5
Z | Gantt Chart | 2022-02-27 | 2022-03-04 | 5
AJ | Measuring Success and Failure in improving TrackR manufacturing process | 2022-02-26 | 2022-03-05 | 7
AI | Possible Future Analysis and Development for TrackR manufacturing process | 2022-02-26 | 2022-03-05 | 7
K | Project Scope Document | 2022-02-25 | 2022-03-05 | 8
AK | Probable Benefits of Changing TrackR manufacturing Process | 2022-02-25 | 2022-03-05 | 8
X | AS-IS Spaghetti Diagram | 2022-02-28 | 2022-03-06 | 6
Y | AS-IS Spaghetti Diagram labels and Notes | 2022-02-28 | 2022-03-06 | 6
W | AS-IS Excel Schedule sheet | 2022-02-28 | 2022-03-06 | 6
L | AS-IS Excel Component sheet | 2022-02-28 | 2022-03-06 | 6
O | AS-IS Excel Assembly Actions,Components,Tests, Failure Rates and Movements sheet | 2022-02-28 | 2022-03-06 | 6
AD | AS-IS Workbook Documentation | 2022-02-27 | 2022-03-07 | 8
AF | AS-IS Profit and Loss Model (P&L) calculations | 2022-02-27 | 2022-03-07 | 8
AG | AS-IS Profit and Loss Model (P&L) income calculations | 2022-02-27 | 2022-03-07 | 8
AH | Detailed References for all Sources of Knowledge | 2022-02-27 | 2022-03-07 | 8
M | AS-IS Excel Component Price sheet with max and min value | 2022-02-28 | 2022-03-08 | 8
AA | AS-IS Daily production sheet | 2022-02-27 | 2022-03-08 | 9
AE | AS-IS Profit and Loss Model (P&L) data | 2022-02-27 | 2022-03-08 | 9
AB | AS-IS Average Production sheet | 2022-02-27 | 2022-03-08 | 9
AC | AS-IS Wholesale sheet | 2022-02-27 | 2022-03-08 | 9
N | AS-IS Excel Picking sheet | 2022-02-26 | 2022-03-08 | 10
V | AS-IS Excel Employee detail sheet | 2022-03-07 | 2022-03-09 | 2
Q | AS-IS Excel Assembly - Component Costs,Totals (Running and Grand) | 2022-02-28 | 2022-03-09 | 9
R | AS-IS Excel Assembly - Labour & Component Costs,Totals (Running and Grand) response to Test fails | 2022-02-28 | 2022-03-09 | 9
S | AS-IS Excel Assembly Movement | 2022-02-28 | 2022-03-09 | 9
P | AS-IS Excel Assembly Assembly - Labour Costs | 2022-02-27 | 2022-03-09 | 10
AM | Six sigma and Failure reduction process report | 2022-03-09 | 2022-03-13 | 4
AL | Suggestion Overview | 2022-03-09 | 2022-03-13 | 4
AO | Siplace Impact and ROI report | 2022-03-09 | 2022-03-15 | 6
AU | Suggestion on Environment Changes | 2022-03-10 | 2022-03-20 | 10
AP | TO BE model - Siplace machine impact | 2022-03-09 | 2022-03-28 | 19
AQ | TO BE Picking process - Financial excel model | 2022-03-09 | 2022-03-28 | 19
AR | TO BE Assembly process - Financial excel model | 2022-03-09 | 2022-03-28 | 19
AS | TO BE Staffing process - Financial excel model | 2022-03-09 | 2022-03-28 | 19
AN | TO BE model - Six sigma process | 2022-03-09 | 2022-03-29 | 20
BY | Powerpoint Presentation | 2022-03-27 | 2022-03-31 | 4
BZ | Final RFI report | 2022-03-25 | 2022-03-31 | 6
AT | Training,Needs and plans | 2022-03-22 | 2022-03-31 | 9
AV | Constraints on Restructuring workspace | 2022-03-20 | 2022-03-31 | 11
BX | Merged Final Report | 2022-03-25 | 2022-03-31 | 6
CA | RACI+, Documentation, Backup Sheets | 2022-02-25 | 2022-04-01 | 35
CB | Time and Effort Reporting | 2022-02-25 | 2022-04-01 | 35
44610
Formulas:
Start date = VLOOKUP([TaskID],'RACI Deliverables'!$C7:O59,11,FALSE)
End Date = VLOOKUP([TaskID],'RACI Deliverables'!$C7:O59,12,FALSE)

## Dlvrbls Day 5-1 (hidden)
Team Task Planning and Assignment Worksheet
Project Team (Assigned Group): |  |  | Team G | Course Week | Day
Date (Worksheet version): |  |  | 2022-01-28
[5 empty] | MayurKumar Rafaliya ( Project Manager) | Prajwal Nayak | Anusha Asokan Palat | Jigeesha Kocher | Cathleen Mathew Mundat | Chaitanya keesari
Deliverable Group |  | DlvID | Project Final Deliverables (RFIs and PM Docs Deliverables are optional) | Need / Requirement ID | MayurKum Plan | Prajwal Plan | Anusha A Plan | Jigeesha Plan | Cathleen Plan | Chaitanya keesari | Professor's Marking Item ID# | Start Date | Due Date (M/D/Y) | Actual Effort Days | Actual Start Date (M/D/Y) | Actual IsBuilt Date (M/D/Y) | Done On Date (M/D/Y)
GA | Building | A | Letter of Transmittal | 20 |  |  | A |  |  |  |  | 2022-01-27 | 2022-01-28 | 1
GA | Building | B | Cover Page | 20 |  |  | R | A |  |  |  | 2022-01-27 | 2022-01-28 | 1
GA | Building | C | Page Headers, Footers and Numbering | 20 | A | R | [5 empty] | 2022-01-27 | 2022-01-28 | 1
GA | Building | D | TOC | 20 |  |  |  | R | A |  |  | 2022-01-27 | 2022-01-28 | 1
GA | Building | E | Document History | 20 |  |  |  |  | R | A |  | 2022-01-27 | 2022-01-28 | 1
GA | Building | F | Executive Summary | 21 |  | A |  |  |  | R |  | 2022-01-27 | 2022-01-28 | 1
GA | Building | G | Assumptions | 21 | R |  |  | A |  |  |  | 2022-01-27 | 2022-01-28 | 1
GA | Building | H | Conclusions | 21 |  | R |  |  |  | A |  | 2022-01-27 | 2022-01-28 | 1
GA | Building | I | Background and overview of client | 22 | A |  | R |  |  |  |  | 2022-01-27 | 2022-01-28 | 1
GA | Building | J | Requests for Information with NDA (included as an Appendix) | 22 |  |  | A | R |  |  |  | 2022-01-20 | 2022-01-21 | 1
GA | Building | K | Project Scope Document | 24 | A | A |  | R |  |  |  | 2022-01-27 | 2022-01-28 | 1
GA | Building | L | AS-IS persons / roles / actors and interactions of Executive Decision Making operations | Need7 | R | A | [5 empty] | 2022-02-03 | 2022-02-07 | 4
GA | Building | M | AS-IS principles of OHT and/or Executive Decision Making operations | Need7 |  |  | R |  | A |  |  | 2022-02-03 | 2022-02-07 | 4
GA | Building | N | To-Be persons / roles / actors and interactions of Executive Decision Making operations | 43 |  |  |  | R |  | A |  | 2022-02-03 | 2022-02-07 | 4
GA | Building | O | Executive Dashboard annotated list of elements for the dashboard, | Need6 | R |  |  |  | A |  |  | 2022-02-05 | 2022-02-08 | 3
GA | Building | P | Possible Future Analysis and Development for Executive Decision Making Process | 43 |  |  | A |  |  | R |  | 2022-02-05 | 2022-02-08 | 3
GA | Building | Q | Measuring Success and Failure in Changing the Executive Decision Making Process | 44 |  | A |  |  | R |  |  | 2022-02-05 | 2022-02-08 | 3
GA | Building | R | Probable Benefits of Changing the Executive Decision Making Process | 46 | A |  | R |  |  |  |  | 2022-02-05 | 2022-02-08 | 3
GA | Building | S | Detailed References | 23 |  |  | R | A |  |  |  | 2022-02-10 | 2022-02-17 | 7
GA | Building | T | Business Challenges | 26 | R |  | A |  |  |  |  | 2022-02-03 | 2022-02-10 | 7
GA | Building | U | Current Brands Involved and their Statuses | 26 |  |  |  |  | A | R |  | 2022-02-03 | 2022-02-06 | 3
GA | Building | V | Executive Dashboard Operation Process - 3+ Risks and Possible Mitigations | 26 |  |  |  | R |  | A |  | 2022-02-04 | 2022-02-10 | 6
GA | Building | W | Known Client Requirements | 41 |  | R |  |  | A |  |  | 2022-01-29 | 2022-02-06 | 8
GA | Building | X | Initial Project Scope in an Appendix, Changes to Scope in a Report Section | 45 |  |  | R | R | A |  |  | 2022-01-27 | 2022-01-28 | 1
GA | Building | Y | Gantt Chart |  | A | R |  |  | R |  |  | 2022-01-27 | 2022-01-28 | 1
GA | Building | Z | Document Quality Check |  | R | A | [5 empty] | 2022-02-15 | 2022-02-17 | 2
GA | Building | AA | USE CASE Diagram(s) for all involved persons, roles, actors, and systems showing their interactions | Need22 |  |  |  | A |  | R |  | 2022-02-04 | 2022-02-07 | 3
GA | Building | AC | Guidance on Using the Dashboard - Video or Text+Graphics | Need7 |  | R |  |  | A |  |  | 2022-02-08 | 2022-02-11 | 3
GA | Building | AD | TrackR Data Gen metric Data Sources List and DB Schema | Need7 | R | [6 empty] | 2022-02-05 | 2022-02-10 | 5
GA | Building | AE | TrackR Data Gen metric Data Sources Data Overview / Profile | Need7 |  | R |  | A |  |  |  | 2022-02-05 | 2022-02-10 | 5
GA | Building | AF | Executive Dashboard Style Guide for Navigation Principles, Colours, Fonts | Need8 |  |  |  | R | A |  |  | 2022-02-06 | 2022-02-10 | 4
GA | Building | AG | Executive Dashboard Navigation Guide using Text, Wireframes and Mockups for Moving forward | Need8 |  | A |  |  |  | R |  | 2022-02-08 | 2022-02-10 | 2
GA | Building | AH | Executive Dashboard Navigation Guide using Text, Wireframes and Mockups for Moving backward | Need8 |  |  | A | R |  |  |  | 2022-02-08 | 2022-02-10 | 2
GA | Building | AI | Executive Dashboard Navigation Guide using Text, Wireframes and Mockups for Changing Time Frames | Need8 |  |  |  | A | R |  |  | 2022-02-08 | 2022-02-10 | 2
GA | Building | AJ | ERD Diagram | 49 | R | A | [5 empty] | 2022-02-04 | 2022-02-08 | 4
GA | Building | AM | Cockburn templates for all identified interactions | Need22 | A |  |  |  |  | R |  | 2022-02-05 | 2022-02-08 | 3
GA | Building | AN | List, References and General Details of Suggested Metrics | Need1 |  | R |  |  |  | A |  | 2022-02-05 | 2022-02-09 | 4
GA | Building | AO | Metric 1 - Data needed, Interpretation, Value to Decision Makers | Need1 | R |  |  |  |  | A |  | 2022-02-05 | 2022-02-09 | 4
GA | Building | AP | Metric 2 - Data needed, Interpretation, Value to Decision Makers | Need1 | A |  |  |  |  | R |  | 2022-02-05 | 2022-02-09 | 4
GA | Building | AQ | Metric 3 - Data needed, Interpretation, Value to Decision Makers | Need1 |  |  |  | A | R |  |  | 2022-02-05 | 2022-02-09 | 4
GA | Building | AR | Metric 4 - Data needed, Interpretation, Value to Decision Makers | Need1 |  |  | R |  | A |  |  | 2022-02-05 | 2022-02-09 | 4
GA | Building | AS | Metric 5 - Data needed, Interpretation, Value to Decision Makers | Need1 |  | R |  |  | A |  |  | 2022-02-05 | 2022-02-09 | 4
GA | Building | AT | Metric 6 - Data needed, Interpretation, Value to Decision Makers | Need1 |  |  | A | R |  |  |  | 2022-02-05 | 2022-02-09 | 4
GA | Building | AU | Interview and/or survey of 6 OHT CPs | Need 2 | R | R | A |  |  |  |  | 2022-02-01 | 2022-02-03 | 2
GA | Building | AV | Data Listing of 6 OHT VPs Measurements of Business Success | Need 2 | A |  | R |  |  |  |  | 2022-02-05 | 2022-02-10 | 5
GA | Building | AW | Data Listing of 6 OHT VPs attitudes toward change, and cooperation in management | Need 2 |  |  | A |  |  | R |  | 2022-02-05 | 2022-02-10 | 5
GA | Building | AX | Data Listing of 6 OHT VPs visions for a better managed OHT | Need 2 |  |  |  |  | R | A |  | 2022-02-05 | 2022-02-10 | 5
GA | Building | AY | Data Listing of 6 OHT VPs Response to Meeting 3 times per week | Need 2 | A |  | R |  |  |  |  | 2022-02-05 | 2022-02-10 | 5
GA | Building | AZ | Interview and/or survey of 6 OHT VPs | Need 3 |  | A |  |  |  | R |  | 2022-02-05 | 2022-02-10 | 5
GA | Building | BA | Data Listing of 6 OHT VPs Monthly Finance Reports Used | Need 3 |  |  |  | R | A |  |  | 2022-02-05 | 2022-02-10 | 5
GA | Building | BB | Listing of 6 OHT VPs Knowledge of Computer Based methods of Report Circulation | Need 3 |  |  |  | A |  | R |  | 2022-02-07 | 2022-02-11 | 4
GA | Building | BC | Listing of 6 OHT VPs Computer Skills, Dashboard Tech Understanding | Need 3 |  | R |  |  |  | A |  | 2022-02-07 | 2022-02-11 | 4
GA | Building | BD | Listing of 6 OHT VPs Preferred learning style | Need 3 |  |  | R | A |  |  |  | 2022-02-07 | 2022-02-11 | 4
GA | Building | BE | Listing of 6 OHT VPs Preferred ways to implement new concepts | Need 3 |  |  |  |  | R | A |  | 2022-02-07 | 2022-02-11 | 4
GA | Building | BF | VP's Written Briefing on Data Lakes, Data Marts, Data Warehouses, including SWOT | Need 4 |  |  | R |  |  | A |  | 2022-02-03 | 2022-02-06 | 3
GA | Building | BG | VP's Written Briefing on ERP. TPS and Query tools, with SWOT | Need 4 |  |  |  | R | A |  |  | 2022-02-03 | 2022-02-06 | 3
GA | Building | BH | VP's Written Briefing on Executive and Analytical Dashboards | Need 4 | R | A | [5 empty] | 2022-02-03 | 2022-02-06 | 3
GA | Building | BI | suggested plan background to implement an Executive Dashboard with 5, at minimum, metrics | Need 5 |  | R |  |  |  | A |  | 2022-02-06 | 2022-02-10 | 4
GA | Building | BJ | suggested plan vision to implement an Executive Dashboard with 5, at minimum, metrics | Need 5 | R |  |  | A |  |  |  | 2022-02-06 | 2022-02-10 | 4
GA | Building | BK | suggested VP training plans | Need 5 | A |  |  |  | R |  |  | 2022-02-11 | 2022-02-15 | 4
GA | Building | BL | suggested plan needs / requirements to implement an Executive Dashboard with 5, at minimum, metrics | Need 5 |  |  |  | A |  | R |  | 2022-02-06 | 2022-02-10 | 4
GA | Building | BM | suggested plan actions to implement an Executive Dashboard with 5, at minimum, metrics | Need 5 |  |  | A | R |  |  |  | 2022-02-06 | 2022-02-10 | 4
GA | Building | BN | suggested plan deliverables to implement an Executive Dashboard with 5, at minimum, metrics | Need 5 |  | A | R |  |  |  |  | 2022-02-06 | 2022-02-10 | 4
GA | Building | BO | suggested plan resources to implement an Executive Dashboard with 5, at minimum, metrics | Need 5 | A |  |  | R |  |  |  | 2022-02-06 | 2022-02-10 | 4
GA | Building | BP | General configuration of Executive Dashboard using PowerBI | Need 6 |  | R | A |  |  |  |  | 2022-02-05 | 2022-02-10 | 5
GF | Closing | CA | RACI+, Documentation, Backup Sheets |  |  | R |  |  | A |  |  | 2022-01-28 | 2022-02-18 | 21
[5 empty] | MayurKum | Prajwal | Anusha A | Jigeesha | Cathleen | Chaitany
|  |  |  | R | 11 | 13 | 12 | 13 | 8 | 11
|  |  |  | A | 11 | 10 | 10 | 11 | 13 | 11
|  |  |  | C | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | MayurKum | Prajwal | Anusha A | Jigeesha | Cathleen | Chaitany

## Tasks Day 5-1 (hidden)
Team Task Planning and Assignment Worksheet
Project Team (Assigned Group): |  |  | Team G | Course Week | Day
Date (Worksheet version): |  |  | 2020-09-17 | 3 | 2
[5 empty] | MayurKumar Rafaliya ( Project Manager) | Prajwal Nayak (RACI Keeper) | Anusha Ashokan Palat | Jigeesha Kocher | Cathleen Mathew Mundat | Chaitanya Keesari | [9 empty] | MayurKumar Rafaliya ( Project Manager) | Prajwal Nayak (RACI Keeper) | Anusha Ashokan Palat | Jigeesha Kocher | Cathleen Mathew Mundat | Chaitanya Keesari
DlvID | TaskID | Project Final Deliverables (No Verb Words at the start) | Activity / Task (VERB: Subject) | Project Phase (see WBS) | MayurKumar | Prajwal | Anusha A | Jigeesha | Cathleen | Chaitany | Start Date | Due Date (M/D/Y) | Actual Effort (Days) | Projected Effort (person - hrs) | Task Type - Team, Single or SubTeam | Task Version | Actual Start Date (M/D/Y) | Done On Date (M/D/Y) | RACI - ACTUAL
A | 1.1 | Letter of Transmittal | Develop a cover page | Create | R |  | A |  |  |  | 2022-02-25 | 2022-02-26 | 1 | 0
A | 1.2 | Letter of Transmittal | Develop a cover page | Pack and publish | R |  | A |  |  |  | 2022-02-25 | 2022-02-26 | 1 | 0
B | 2.1 | Cover Page | Develop a cover letter | Create |  |  | R | A |  |  | 2022-02-25 | 2022-02-26 | 1 | 0 |  |  |  |  | R | C | C
B | 2.2 | Cover Page | Develop a cover letter | Pack and publish |  |  | R | A |  |  | 2022-02-25 | 2022-02-26 | 1 | 0
C | 3.1 | Page Headers, Footers and Numbering | Develop a header, footer and numbering | Create | A | R |  |  |  |  | 2022-02-25 | 2022-02-26 | 1 | 0
C | 3.2 | Page Headers, Footers and Numbering | Develop header, footer and numbering | Pack and publish | A | R |  |  |  |  | 2022-02-25 | 2022-02-26 | 1 | 0
D | 4.1 | TOC | Create a table of content | Publish |  |  |  | R | A |  | 2022-02-25 | 2022-02-26 | 1 | 0
E | 5.1 | Document History | Research about documnent history document | Research |  |  |  |  | R | A | 2022-02-25 | 2022-02-26 | 1 | 0
E | 5.2 | Document History | Develoop document history document | Create |  |  |  |  | R | A | 2022-02-25 | 2022-02-26 | 1 | 0
E | 5.3 | Document History | Publish document history document | Publish |  |  |  |  | R | A | 2022-02-25 | 2022-02-26 | 1 | 0
F | 6.1 | Executive Summary | Write summary for executives | Create |  |  | R |  |  | A | 2022-02-25 | 2022-02-26 | 1 | 0
F | 6.2 | Executive Summary | publish summary for executive summary | Publish |  |  | R |  |  | A | 2022-02-25 | 2022-02-26 | 1 | 0
G | 7.1 | Assumptions | Gather assumptions | Research | R |  |  | A |  |  | 2022-02-25 | 2022-02-26 | 1 | 0
G | 7.2 | Assumptions | Create asuumptions | Create | R |  |  | A |  |  | 2022-02-25 | 2022-02-26 | 1 | 0
G | 7.3 | Assumptions | Publish assumptions | Pack and publish | R |  |  | A |  |  | 2022-02-25 | 2022-02-26 | 1 | 0
H | 8.1 | Conclusions | Create conclusion | Create |  | R |  |  |  | A | 2022-02-25 | 2022-02-26 | 1 | 0
H | 8.2 | Conclusions | Publish conclusion | Publish |  | R |  |  |  | A | 2022-02-25 | 2022-02-26 | 1 | 0
I | 9.1 | Background and overview of client | Develop document | Create | A |  | R |  |  |  | 2022-02-25 | 2022-02-26 | 1 | 0
I | 9.2 | Background and overview of client | Publish final document | Publish | A |  | R |  |  |  | 2022-02-25 | 2022-02-26 | 1 | 0
J | 10.1 | Requests for Information with NDA (included as an Appendix) | Create RFI Document | Create |  |  | A | R |  |  | 2022-02-25 | 2022-02-26 | 1 | 0
J | 10.2 | Requests for Information with NDA (included as an Appendix) | Look out for questions need to ask | Research |  |  | A | R |  |  | 2022-02-25 | 2022-02-26 | 1 | 0
J | 10.3 | Requests for Information with NDA (included as an Appendix) | Prepare Final RFI Document | Pack and publish |  |  | A | R |  |  | 2022-02-25 | 2022-02-26 | 1 | 0
K | 11.1 | Project Scope Document | Creating Document | Create | A | A |  | R |  |  | 2022-02-25 | 2022-03-05 | 8 | 0
K | 11.2 | Project Scope Document | Develop content for scope | Research | A | A |  | R |  |  | 2022-02-25 | 2022-03-05 | 8 | 0
K | 11.3 | Project Scope Document | Finalize and publish | Pack and publish | A | A |  | R |  |  | 2022-02-25 | 2022-03-05 | 8 | 0
L | 12.1 | AS-IS persons / roles / actors and interactions of Executive Decision Making operations | Interview VPs | Create | R | A |  |  |  |  | 2022-02-28 | 2022-03-06 | 6 | 0
L | 12.2 | AS-IS persons / roles / actors and interactions of Executive Decision Making operations | Prepare interactions flow of decision | Research | R | A |  |  |  |  | 2022-02-28 | 2022-03-06 | 6 | 0
L | 12.3 | AS-IS persons / roles / actors and interactions of Executive Decision Making operations | Publish and finalize | Pack and publish | R | A |  |  |  |  | 2022-02-28 | 2022-03-06 | 6 | 0
M | 13.1 | AS-IS Excel Component Price sheet with max and min value | Interview VPs | Create |  |  | R |  | A |  | 2022-02-28 | 2022-03-08 | 8 | 0
M | 13.2 | AS-IS Excel Component Price sheet with max and min value | Prepare Decision flow | Research |  |  | R |  | A |  | 2022-02-28 | 2022-03-08 | 8 | 0
M | 13.3 | AS-IS Excel Component Price sheet with max and min value | Publish and finalize | Package and publish |  |  | R |  | A |  | 2022-02-28 | 2022-03-08 | 8 | 0
N | 14.1 | AS-IS Excel Picking sheet | Develop To-be flow | Create |  |  |  | R |  | A | 2022-02-26 | 2022-03-08 | 10 | 0
N | 14.2 | AS-IS Excel Picking sheet | Prepare interactions flow between actors/roles/system | Research |  |  |  | R |  | A | 2022-02-26 | 2022-03-08 | 10 | 0
N | 14.3 | AS-IS Excel Picking sheet | Publish and finalize | Package and publish |  |  |  | R |  | A | 2022-02-26 | 2022-03-08 | 10 | 0
O | 15.1 | AS-IS Excel Assembly Actions,Components,Tests, Failure Rates and Movements sheet | Develop list | Create | R |  |  |  | A |  | 2022-02-28 | 2022-03-06 | 6 | 0
O | 15.2 | AS-IS Excel Assembly Actions,Components,Tests, Failure Rates and Movements sheet | Publish | Package and publish | R |  |  |  | A |  | 2022-02-28 | 2022-03-06 | 6 | 0
p | 16.1 | AS-IS Excel Assembly Assembly - Labour Costs | Develop Document | Create |  |  | A |  |  | R | 2022-02-27 | 2022-03-09 | 10 | 0
p | 16.2 | AS-IS Excel Assembly Assembly - Labour Costs | Analyse and collect information | Research |  |  | A |  |  | R | 2022-02-27 | 2022-03-09 | 10 | 0
P | 16.3 | AS-IS Excel Assembly Assembly - Labour Costs | Finalize and publish | Package and publish |  |  | A |  |  | R | 2022-02-27 | 2022-03-09 | 10 | 0
Q | 17.1 | AS-IS Excel Assembly - Component Costs,Totals (Running and Grand) | Develop Document | Create |  | A |  |  | R |  | 2022-02-28 | 2022-03-09 | 9 | 0
Q | 17.2 | AS-IS Excel Assembly - Component Costs,Totals (Running and Grand) | Analyse and collect information | Research |  | A |  |  | R |  | 2022-02-28 | 2022-03-09 | 9 | 0
Q | 17.3 | AS-IS Excel Assembly - Component Costs,Totals (Running and Grand) | Finalize and publish | Package and publish |  | A |  |  | R |  | 2022-02-28 | 2022-03-09 | 9 | 0
R | 18.1 | AS-IS Excel Assembly - Labour & Component Costs,Totals (Running and Grand) response to Test fails | Develop Document | Create | A |  | R |  |  |  | 2022-02-28 | 2022-03-09 | 9 | 0
R | 18.2 | AS-IS Excel Assembly - Labour & Component Costs,Totals (Running and Grand) response to Test fails | Analyse and collect information | Research | A |  | R |  |  |  | 2022-02-28 | 2022-03-09 | 9 | 0
R | 18.3 | AS-IS Excel Assembly - Labour & Component Costs,Totals (Running and Grand) response to Test fails | Finalize and publish | Package and publish | A |  | R |  |  |  | 2022-02-28 | 2022-03-09 | 9 | 0
S | 19.1 | AS-IS Excel Assembly Movement | Develop Document | Create |  |  | R | A |  |  | 2022-02-28 | 2022-03-09 | 9 | 0
S | 19.2 | AS-IS Excel Assembly Movement | Finalize and publish | Package and publish |  |  | R | A |  |  | 2022-02-28 | 2022-03-09 | 9 | 0
T | 20.1 | Business Challenges | Develop Document | Create | R |  | A |  |  |  | 2022-02-27 | 2022-03-04 | 5 | 0
T | 20.2 | Business Challenges | Analyse and collect information | Research | R |  | A |  |  |  | 2022-02-27 | 2022-03-04 | 5 | 0
T | 20.3 | Business Challenges | Finalize and publish | Package and publish | R |  | A |  |  |  | 2022-02-27 | 2022-03-04 | 5 | 0
U | 21.1 | Current Brands Involved and their Statuses | Develop Document | Create |  |  |  |  | A | R | 2022-02-27 | 2022-03-04 | 5 | 0
U | 21.2 | Current Brands Involved and their Statuses | Analyse and collect information | Research |  |  |  |  | A | R | 2022-02-27 | 2022-03-04 | 5 | 0
U | 21.3 | Current Brands Involved and their Statuses | Finalize and publish | Package and publish |  |  |  |  | A | R | 2022-02-27 | 2022-03-04 | 5 | 0
V | 22.1 | AS-IS Excel Employee detail sheet | Develop Document | Create |  |  |  | R |  | A | 2022-03-07 | 2022-03-09 | 2 | 0
V | 22.2 | AS-IS Excel Employee detail sheet | Analyse and list out possible risks | Research |  |  |  | R |  | A | 2022-03-07 | 2022-03-09 | 2 | 0
V | 22.3 | AS-IS Excel Employee detail sheet | Finalize and publish | Package and publish |  |  |  | R |  | A | 2022-03-07 | 2022-03-09 | 2 | 0
W | 23.1 | AS-IS Excel Schedule sheet | Develop Document | Create |  | R |  |  | A |  | 2022-02-28 | 2022-03-06 | 6 | 0
w | 23.2 | AS-IS Excel Schedule sheet | Finalize and publish | Package and publish |  | R |  |  | A |  | 2022-02-28 | 2022-03-06 | 6 | 0
X | 24.1 | AS-IS Spaghetti Diagram | Develop Document | Create |  |  | R | R | A |  | 2022-02-28 | 2022-03-06 | 6 | 0
X | 24.2 | AS-IS Spaghetti Diagram | Analyse and document | Research |  |  | R | R | A |  | 2022-02-28 | 2022-03-06 | 6 | 0
X | 24.3 | AS-IS Spaghetti Diagram | Finalize and publish | Package and publish |  |  | R | R | A |  | 2022-02-28 | 2022-03-06 | 6 | 0
Y | 25.1 | AS-IS Spaghetti Diagram labels and Notes | Develop Document | Create | A | R |  |  | R |  | 2022-02-28 | 2022-03-06 | 6 | 0
Y | 25.2 | AS-IS Spaghetti Diagram labels and Notes | Analyse and plan | Research | A | R |  |  | R |  | 2022-02-28 | 2022-03-06 | 6 | 0
Y | 25.3 | AS-IS Spaghetti Diagram labels and Notes | Finalize and publish | Package and publish | A | R |  |  | R |  | 2022-02-28 | 2022-03-06 | 6 | 0
Z | 26.1 | Gantt Chart | Develop Document | Create |  | A |  |  | R |  | 2022-02-27 | 2022-03-04 | 5 | 0
Z | 26.2 | Gantt Chart | Finalize and publish | Package and publish |  | A |  |  | R |  | 2022-02-27 | 2022-03-04 | 5 | 0
AA | 27.1 | AS-IS Daily production sheet | Develop Use case Document | Create |  |  |  | A |  | R | 2022-02-27 | 2022-03-08 | 9 | 0
AA | 27.2 | AS-IS Daily production sheet | Analyse and list out relation between actors and systems | Research |  |  |  | A |  | R | 2022-02-27 | 2022-03-08 | 9 | 0
AA | 27.3 | AS-IS Daily production sheet | Finalize and publish | Package and publish |  |  |  | A |  | R | 2022-02-27 | 2022-03-08 | 9 | 0
AC | 29.1 | AS-IS Wholesale sheet | Record video for using dashboard | Create |  | R |  |  | A |  | 2022-02-27 | 2022-03-08 | 9 | 0
AC | 29.2 | AS-IS Wholesale sheet | Show step by step guidance on using dashboard | Research |  | R |  |  | A |  | 2022-02-27 | 2022-03-08 | 9 | 0
AC | 29.3 | AS-IS Wholesale sheet | Finalize and publish | Package and publish |  | R |  |  | A |  | 2022-02-27 | 2022-03-08 | 9 | 0
AD | 30.1 | AS-IS Workbook Documentation | Create source list | Create | R | [5 empty] | 2022-02-27 | 2022-03-07 | 8 | 0
AD | 30.2 | AS-IS Workbook Documentation | analyze and collect information | Research | R | [5 empty] | 2022-02-27 | 2022-03-07 | 8 | 0
AD | 30.3 | AS-IS Workbook Documentation | Publish | Package and publish | R | [5 empty] | 2022-02-27 | 2022-03-07 | 8 | 0
AE | 31.1 | AS-IS Profit and Loss Model (P&L) data | Create source list | Create |  | R |  | A |  |  | 2022-02-27 | 2022-03-08 | 9 | 0
AE | 31.2 | AS-IS Profit and Loss Model (P&L) data | Publish | Package and publish |  | R |  | A |  |  | 2022-02-27 | 2022-03-08 | 9 | 0
AF | 32.1 | AS-IS Profit and Loss Model (P&L) calculations | Create document for style guide | Create |  | R |  |  | A |  | 2022-02-27 | 2022-03-07 | 8 | 0
AF | 32.2 | AS-IS Profit and Loss Model (P&L) calculations | Prepare and Finalize | Package and publish |  | R |  |  | A |  | 2022-02-27 | 2022-03-07 | 8 | 0
AG | 33.1 | AS-IS Profit and Loss Model (P&L) income calculations | Create navigation guide wireframe for moving forward | Create |  | A |  |  |  | R | 2022-02-27 | 2022-03-07 | 8 | 0
AG | 33.2 | AS-IS Profit and Loss Model (P&L) income calculations | Prepare layout and finalize | Package and publish |  | A |  |  |  | R | 2022-02-27 | 2022-03-07 | 8 | 0
AH | 34.1 | Detailed References for all Sources of Knowledge | Create navigation guide wireframe for moving backward | Create |  |  | A | R |  |  | 2022-02-27 | 2022-03-07 | 8 | 0
AH | 34.2 | Detailed References for all Sources of Knowledge | Prepare layout and finalize | Package and publish |  |  | A | R |  |  | 2022-02-27 | 2022-03-07 | 8 | 0
AI | 35.1 | Possible Future Analysis and Development for TrackR manufacturing process | Create navigation guide wireframe for Changing time frame | Create |  |  |  | A | R |  | 2022-02-26 | 2022-03-05 | 7 | 0
AI | 35.2 | Possible Future Analysis and Development for TrackR manufacturing process | Prepare layout and finalize | Package and publish |  |  |  | A | R |  | 2022-02-26 | 2022-03-05 | 7 | 0
AJ | 36.1 | Measuring Success and Failure in improving TrackR manufacturing process | Develop document | Create | R | A |  |  |  |  | 2022-02-26 | 2022-03-05 | 7 | 0
AJ | 36.2 | Measuring Success and Failure in improving TrackR manufacturing process | Analyze and prepare erd layout | Research | R | A |  |  |  |  | 2022-02-26 | 2022-03-05 | 7 | 0
AJ | 36.3 | Measuring Success and Failure in improving TrackR manufacturing process | Finalize and publish | Package and publish | R | A |  |  |  |  | 2022-02-26 | 2022-03-05 | 7 | 0
AM | 39.1 | Six sigma and Failure reduction process report | Develop Cockburn template | Create | R |  |  |  |  | A | 2022-03-09 | 2022-03-13 | 4 | 0
AM | 39.2 | Six sigma and Failure reduction process report | Analyze and collect information | Research | R |  |  |  |  | A | 2022-03-09 | 2022-03-13 | 4 | 0
AM | 39.3 | Six sigma and Failure reduction process report | Finalize and publish | Package and publish | R |  |  |  |  | A | 2022-03-09 | 2022-03-13 | 4 | 0
AN | 40.1 | TO BE model - Six sigma process | Create general details of suggested metrics | Create | R | A |  |  |  |  | 2022-03-09 | 2022-03-29 | 20 | 0
AN | 40.2 | TO BE model - Six sigma process | Collect all information | Research | R | A |  |  |  |  | 2022-03-09 | 2022-03-29 | 20 | 0
AN | 40.3 | TO BE model - Six sigma process | Finalize and publish | Package and publish | R | A |  |  |  |  | 2022-03-09 | 2022-03-29 | 20 | 0
AO | 41.1 | Siplace Impact and ROI report | Develop document for Metric 1 | Create | R |  | A |  | R |  | 2022-03-09 | 2022-03-15 | 6 | 0
AO | 41.2 | Siplace Impact and ROI report | Analyze and identify metric | Research | R |  | A |  | R |  | 2022-03-09 | 2022-03-15 | 6 | 0
AO | 41.3 | Siplace Impact and ROI report | Prepare and Finalize | Package and publish | R |  | A |  | R |  | 2022-03-09 | 2022-03-15 | 6 | 0
AP | 42.1 | TO BE model - Siplace machine impact | Develop document for Metric 2 | Create | A |  | A |  | R |  | 2022-03-09 | 2022-03-28 | 19 | 0
AP | 42.2 | TO BE model - Siplace machine impact | Analyze and identify metric | Research | A |  | A |  | R |  | 2022-03-09 | 2022-03-28 | 19 | 0
AP | 42.3 | TO BE model - Siplace machine impact | Prepare and Finalize | Package and publish | A |  | A |  | R |  | 2022-03-09 | 2022-03-28 | 19 | 0
AQ | 43.1 | TO BE Picking process - Financial excel model | Develop document for Metric 3 | Create |  | R |  | A |  |  | 2022-03-09 | 2022-03-28 | 19 | 0
AQ | 43.2 | TO BE Picking process - Financial excel model | Analyze and identify metric | Research |  | R |  | A |  |  | 2022-03-09 | 2022-03-28 | 19 | 0
AQ | 43.3 | TO BE Picking process - Financial excel model | Prepare and Finalize | Package and publish |  | R |  | A |  |  | 2022-03-09 | 2022-03-28 | 19 | 0
AR | 44.1 | TO BE Assembly process - Financial excel model | Develop document for Metric 4 | Create |  |  |  | R |  | R | 2022-03-09 | 2022-03-28 | 19 | 0 |  |  | 2017-09-08 | 2017-09-08 | R | R | R | R | R
AR | 44.2 | TO BE Assembly process - Financial excel model | Analyze and identify metric | Research |  |  |  | R |  | R | 2022-03-09 | 2022-03-28 | 19 | 0
AR | 44.3 | TO BE Assembly process - Financial excel model | Prepare and Finalize | Package and publish |  |  |  | R |  | R | 2022-03-09 | 2022-03-28 | 19 | 0
AS | 45.1 | TO BE Staffing process - Financial excel model | Develop document for Metric 5 | Create |  |  | R |  |  | A | 2022-03-09 | 2022-03-28 | 19 | 0 |  |  | 2017-09-14 | 2017-09-14 | R | R | Absent | R | R
As | 45.2 | TO BE Staffing process - Financial excel model | Analyze and identify metric | Research |  |  | R |  |  | A | 2022-03-09 | 2022-03-28 | 19 | 0
AS | 45.3 | TO BE Staffing process - Financial excel model | Prepare and Finalize | Package and publish |  |  | R |  |  | A | 2022-03-09 | 2022-03-28 | 19 | 0
AT | 46.1 | Training,Needs and plans | Develop document for Metric 6 | Create |  |  |  |  | A | R | 2022-03-22 | 2022-03-31 | 9 | 0
AT | 46.2 | Training,Needs and plans | Analyze and identify metric | Research |  |  |  |  | A | R | 2022-03-22 | 2022-03-31 | 9 | 0
AT | 46.3 | Training,Needs and plans | Prepare and Finalize | Package and publish |  |  |  |  | A | R | 2022-03-22 | 2022-03-31 | 9 | 0
AU | 47.1 | Suggestion on Environment Changes | Develop document | Create |  | A | R |  |  |  | 2022-03-10 | 2022-03-20 | 10 | 0
AU | 47.2 | Suggestion on Environment Changes | Finalize document | Publish |  | A | R |  |  |  | 2022-03-10 | 2022-03-20 | 10 | 0
AV | 48.1 | Constraints on Restructuring workspace | Develop document for business success | Create | A |  |  |  | R |  | 2022-03-20 | 2022-03-31 | 11 | 0
AV | 48.2 | Constraints on Restructuring workspace | Analyse and collect information | Research | A |  |  |  | R |  | 2022-03-20 | 2022-03-31 | 11 | 0
AV | 48.3 | Constraints on Restructuring workspace | Finalize and Publish | Package and Publish | A |  |  |  | R |  | 2022-03-20 | 2022-03-31 | 11 | 0
AW | 49.1 | #N/A | Develop document for attitude towards change | Create | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
AW | 49.2 | #N/A | Analyse and collect information | Research | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
AW | 49.3 | #N/A | Finalize and Publish | Package and Publish | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
AX | 50.1 | #N/A | Develop document for OHT's vision for better management | Create | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
AX | 50.2 | #N/A | Analyse and collect information | Research | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
AX | 50.3 | #N/A | Finalize and Publish | Package and Publish | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
AY | 51.1 | #N/A | Develop document for response to meeting 3 times a week | Create | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
AY | 51.2 | #N/A | Analyse and collect information | Research | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
AY | 51.3 | #N/A | Finalize and Publish | Package and Publish | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
AZ | 52.1 | #N/A | Develop document | Create | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
AZ | 52.2 | #N/A | Finalize document | Publish | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
BA | 53.1 | #N/A | Gather the infromation about Monthly Finance Reports used | Research | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
BA | 53.2 | #N/A | Document the infromation | Create | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
BA | 53.3 | #N/A | Finalise the report | Publish | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
BB | 54.1 | #N/A | Gather the knowledge about the Computer Based methods of Report Circulation | Research | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
BB | 54.2 | #N/A | List the knowledge about the Computer Based methods of Report Circulation | Create | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
BB | 54.3 | #N/A | Publish the knowledge | Publish | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
BC | 55.1 | #N/A | Gather information about the computer skills, Dashboard understanding | Research | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
BC | 55.2 | #N/A | analyse information about the computer skills, Dashboard understanding | Create | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
BC | 55.3 | #N/A | Document the learning | Pack and Publish | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
BD | 56.1 | #N/A | Eliciate the preferred way of learning a new concept from VP | Research | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
BD | 56.2 | #N/A | identify the way of learning | Create | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
BD | 56.3 | #N/A | Pack and publish preferred way of learning | Pack and Publish | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
BE | 57.1 | #N/A | Eliciate the preferred way of implement a new concept from VP | Research | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
BE | 57.2 | #N/A | Identify the way of implementation | Pack and Publish | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
BE | 57.3 | #N/A | Share it with a team | Pack and ublish | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
BF | 58.1 | #N/A | Research about the Data lakes, Data Marts, Data Warehouse, including SWOT | Research | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
BF | 58.2 | #N/A | Create about the Data lakes, Data Marts, Data Warehouse, including SWOT | Create | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
BF | 58.3 | #N/A | Pack and Publish the writtern briefing about Data lakes, Data Marts, Data Warehouse, including SWOT | Pack and publish | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
BG | 59.1 | #N/A | Research about the ERP, TPS and Query tools with SWOT | Research | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
BG | 59.2 | #N/A | Create about the ERP, TPS and Query tools with SWOT | Create | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
BG | 59.3 | #N/A | Pack and Publish the wirtten briefing about ERP, TPS and Query tools with SWOT | Pack and Publish | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
BH | 60.1 | #N/A | Reserach about the analytical dashboard and Executive dashboard | Research | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
BH | 60.2 | #N/A | Create a report explaning analytical dashboard and Executive dashboard | Create | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
BH | 60.3 | #N/A | Pack and Publish the Report | Pack and publish | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
BI | 61.1 | #N/A | Research and Plan about the implementation plan | Research | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
BI | 61.2 | #N/A | Create a implementation plan | Create | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
BI | 61.3 | #N/A | Execute the implementation plan | Pack and Publish | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
BJ | 62.1 | #N/A | Research and Plan about the implementation plan | Research | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
BJ | 62.2 | #N/A | Create a implementation plan | Create | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
BJ | 62.3 | #N/A | Execute the implementation plan | Pack and Publish | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
BK | 63.1 | #N/A | Research about the Training plan | Research | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
BK | 63.2 | #N/A | Create a Training plan | Create | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
BK | 63.3 | #N/A | Execute the training plan | Execute | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
BL | 64.1 | #N/A | Research and Plan about the implementation plan | Research | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
BL | 64.2 | #N/A | Create a implementation plan | Create | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
BL | 64.3 | #N/A | Execute the implementation plan | Execute | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
BM | 65.1 | #N/A | Research and Plan about the implementation plan | Research | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
BM | 65.2 | #N/A | Create a implementation plan | Create | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
BM | 65.3 | #N/A | Execute the implementation plan | Execute | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
BN | 66.1 | #N/A | Research and Plan about the implementation plan | Research | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
BN | 66.2 | #N/A | Create a implementation plan | Create | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
BN | 66.3 | #N/A | Execute the implementation plan | Execute | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
BO | 67.1 | #N/A | Research and Plan about the implementation plan | Research | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
BO | 67.2 | #N/A | Create a implementation plan | Create | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
BO | 67.3 | #N/A | Execute the implementation plan | Execute | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
BP | 68.1 | #N/A | Research about the General configuration of Executive Dashboard using PowerBI | Research | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
BP | 68.2 | #N/A | Create about the General configuration of Executive Dashboard using PowerBI | Create | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
BP | 68.3 | #N/A | Pack and Publish General configuration of Executive Dashboard using PowerBI | Pack and Publish | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
CA | 79.1 | RACI+, Documentation, Backup Sheets | Create a RACI+, Documentation and Backup Sheets | Research |  | R |  |  | A |  | 2022-02-25 | 2022-04-01 | 35 | 0
CA | 79.2 | RACI+, Documentation, Backup Sheets | Create a RACI+, Documentation and Backup Sheets | Create |  | R |  |  | A |  | 2022-02-25 | 2022-04-01 | 35 | 0
CA | 79.3 | RACI+, Documentation, Backup Sheets | Create a RACI+, Documentation and Backup Sheets | Pack and Publish |  | R |  |  | A |  | 2022-02-25 | 2022-04-01 | 35 | 0
[8 empty] | MayurKum | Prajwal | Anusha A | Jigeesha | Cathleen | Chaitany
[6 empty] | Analysis of Plan R, A, C, I's: | R | 28 | 22 | 22 | 21 | 22 | 17
[7 empty] | A | 19 | 21 | 19 | 17 | 25 | 19
[7 empty] | C | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | I | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | MayurKum | Prajwal | Anusha A | Jigeesha | Cathleen | Chaitany

## Total Efforts
Person 1 Time Tracking
RowID | Team Member | Date | TaskID | StartTime | Duration | StartTime | EndTime | Duration | Complete% | Comments
5 | [7 empty] | 0
6 | [7 empty] | 0
7 | [7 empty] | 0
8 | [7 empty] | 0
9 | [7 empty] | 0
10 | [7 empty] | 0
11 | [7 empty] | 0
12 | [7 empty] | 0
13 | [7 empty] | 0
14 | [7 empty] | 0
15 | [7 empty] | 0
16 | [7 empty] | 0
17 | [7 empty] | 0
18 | [7 empty] | 0
19 | [7 empty] | 0
20 | [7 empty] | 0
21 | [7 empty] | 0
22 | [7 empty] | 0
23 | [7 empty] | 0
24 | [7 empty] | 0
25 | [7 empty] | 0
26 | [7 empty] | 0
27 | [7 empty] | 0
28 | [7 empty] | 0
29 | [7 empty] | 0
30 | [7 empty] | 0
31 | [7 empty] | 0
32 | [7 empty] | 0
33 | [7 empty] | 0
34 | [7 empty] | 0
35 | [7 empty] | 0
36 | [7 empty] | 0
37 | [7 empty] | 0
38 | [7 empty] | 0
39 | [7 empty] | 0
40 | [7 empty] | 0
41 | [7 empty] | 0
42 | [7 empty] | 0
43 | [7 empty] | 0
44 | [7 empty] | 0
45 | [7 empty] | 0
46 | [7 empty] | 0
47 | [7 empty] | 0
48 | [7 empty] | 0
49 | [7 empty] | 0
50 | [7 empty] | 0
51 | [7 empty] | 0
52 | [7 empty] | 0
53 | [7 empty] | 0
54 | [7 empty] | 0
55 | [7 empty] | 0
56 | [7 empty] | 0
57 | [7 empty] | 0
58 | [7 empty] | 0
59 | [7 empty] | 0
60 | [7 empty] | 0
61 | [7 empty] | 0
62 | [7 empty] | 0
63 | [7 empty] | 0
64 | [7 empty] | 0
65 | [7 empty] | 0
66 | [7 empty] | 0
67 | [7 empty] | 0
68 | [7 empty] | 0
69 | [7 empty] | 0
70 | [7 empty] | 0
71 | [7 empty] | 0
72 | [7 empty] | 0
73 | [7 empty] | 0
74 | [7 empty] | 0
75 | [7 empty] | 0
76 | [7 empty] | 0
77 | [7 empty] | 0
78 | [7 empty] | 0
79 | [7 empty] | 0
80 | [7 empty] | 0
81 | [7 empty] | 0
82 | [7 empty] | 0
83 | [7 empty] | 0
84 | [7 empty] | 0
85 | [7 empty] | 0
86 | [7 empty] | 0
87 | [7 empty] | 0
88 | [7 empty] | 0
89 | [7 empty] | 0
90 | [7 empty] | 0
91 | [7 empty] | 0
92 | [7 empty] | 0
93 | [7 empty] | 0
94 | [7 empty] | 0
95 | [7 empty] | 0
96 | [7 empty] | 0
97 | [7 empty] | 0
98 | [7 empty] | 0
99 | [7 empty] | 0
100 | [7 empty] | 0
101 | [7 empty] | 0
102 | [7 empty] | 0
103 | [7 empty] | 0
104 | [7 empty] | 0
105 | [7 empty] | 0
106 | [7 empty] | 0
107 | [7 empty] | 0
108 | [7 empty] | 0
109 | [7 empty] | 0
110 | [7 empty] | 0
111 | [7 empty] | 0
112 | [7 empty] | 0
113 | [7 empty] | 0
114 | [7 empty] | 0
115 | [7 empty] | 0
116 | [7 empty] | 0
117 | [7 empty] | 0
118 | [7 empty] | 0
119 | [7 empty] | 0
120 | [7 empty] | 0
121 | [7 empty] | 0
122 | [7 empty] | 0
123 | [7 empty] | 0
124 | [7 empty] | 0
125 | [7 empty] | 0
126 | [7 empty] | 0
127 | [7 empty] | 0
128 | [7 empty] | 0
129 | [7 empty] | 0
130 | [7 empty] | 0
131 | [7 empty] | 0
132 | [7 empty] | 0
133 | [7 empty] | 0
134 | [7 empty] | 0
135 | [7 empty] | 0
136 | [7 empty] | 0
137 | [7 empty] | 0
138 | [7 empty] | 0
139 | [7 empty] | 0
140 | [7 empty] | 0
141 | [7 empty] | 0
142 | [7 empty] | 0
143 | [7 empty] | 0
144 | [7 empty] | 0
145 | [7 empty] | 0
146 | [7 empty] | 0
147 | [7 empty] | 0
148 | [7 empty] | 0
149 | [7 empty] | 0
150 | [7 empty] | 0
151 | [7 empty] | 0
152 | [7 empty] | 0
153 | [7 empty] | 0
154 | [7 empty] | 0
155 | [7 empty] | 0
156 | [7 empty] | 0
157 | [7 empty] | 0
158 | [7 empty] | 0
159 | [7 empty] | 0
160 | [7 empty] | 0
161 | [7 empty] | 0
162 | [7 empty] | 0
163 | [7 empty] | 0
164 | [7 empty] | 0
165 | [7 empty] | 0
166 | [7 empty] | 0
167 | [7 empty] | 0
168 | [7 empty] | 0
169 | [7 empty] | 0
170 | [7 empty] | 0
171 | [7 empty] | 0
172 | [7 empty] | 0
173 | [7 empty] | 0
174 | [7 empty] | 0
175 | [7 empty] | 0
176 | [7 empty] | 0
177 | [7 empty] | 0
178 | [7 empty] | 0
179 | [7 empty] | 0
180 | [7 empty] | 0
181 | [7 empty] | 0
182 | [7 empty] | 0
183 | [7 empty] | 0
184 | [7 empty] | 0
185 | [7 empty] | 0
186 | [7 empty] | 0
187 | [7 empty] | 0
188 | [7 empty] | 0
189 | [7 empty] | 0
190 | [7 empty] | 0
191 | [7 empty] | 0
192 | [7 empty] | 0
193 | [7 empty] | 0
194 | [7 empty] | 0
195 | [7 empty] | 0
196 | [7 empty] | 0
197 | [7 empty] | 0
198 | [7 empty] | 0
199 | [7 empty] | 0
200 | [7 empty] | 0
201 | [7 empty] | 0
202 | [7 empty] | 0
203 | [7 empty] | 0
204 | [7 empty] | 0
205 | [7 empty] | 0
206 | [7 empty] | 0
207 | [7 empty] | 0
208 | [7 empty] | 0
209 | [7 empty] | 0
210 | [7 empty] | 0
211 | [7 empty] | 0
212 | [7 empty] | 0
213 | [7 empty] | 0
214 | [7 empty] | 0
215 | [7 empty] | 0
216 | [7 empty] | 0
217 | [7 empty] | 0
218 | [7 empty] | 0
219 | [7 empty] | 0
220 | [7 empty] | 0
221 | [7 empty] | 0
222 | [7 empty] | 0
223 | [7 empty] | 0
224 | [7 empty] | 0
225 | [7 empty] | 0
226 | [7 empty] | 0
227 | [7 empty] | 0
228 | [7 empty] | 0
229 | [7 empty] | 0
230 | [7 empty] | 0
231 | [7 empty] | 0
232 | [7 empty] | 0
233 | [7 empty] | 0
234 | [7 empty] | 0
235 | [7 empty] | 0
236 | [7 empty] | 0
237 | [7 empty] | 0
238 | [7 empty] | 0
239 | [7 empty] | 0
240 | [7 empty] | 0
241 | [7 empty] | 0
242 | [7 empty] | 0
243 | [7 empty] | 0
244 | [7 empty] | 0
245 | [7 empty] | 0
246 | [7 empty] | 0
247 | [7 empty] | 0
248 | [7 empty] | 0

## PRAJWAL
Prajwal's Time Tracking
|  |  | Plan | (hrs) | Actual |  | (hrs)
Row | Date | ActivityID | StartTime | Duration | StartTime | EndTime | Duration | Complete% | Comments
5 | [6 empty] | 0
6 | [6 empty] | 0
7 | [6 empty] | 0
8 | [6 empty] | 0
0
10 | [6 empty] | 0
11 | [6 empty] | 0
12 | [6 empty] | 0
13 | [6 empty] | 0
14 | [6 empty] | 0
15 | [6 empty] | 0
16 | [6 empty] | 0
17 | [6 empty] | 0
18 | [6 empty] | 0
19 | [6 empty] | 0
20 | [6 empty] | 0
21 | [6 empty] | 0
22
23 | [6 empty] | 0
24 | [6 empty] | 0
25 | [6 empty] | 0
26 | [6 empty] | 0
27 | [6 empty] | 0
28 | [6 empty] | 0
29 | [6 empty] | 0
30 | [6 empty] | 0
31 | [6 empty] | 0
32 | [6 empty] | 0
33 | [6 empty] | 0
34 | [6 empty] | 0
35 | [6 empty] | 0
36 | [6 empty] | 0
37 | [6 empty] | 0
38 | [6 empty] | 0
39 | [6 empty] | 0
40 | [6 empty] | 0
41 | [6 empty] | 0
42 | [6 empty] | 0
43 | [6 empty] | 0
44 | [6 empty] | 0
45 | [6 empty] | 0
46 | [6 empty] | 0
47 | [6 empty] | 0
48 | [6 empty] | 0
49 | [6 empty] | 0
50 | [6 empty] | 0
51 | [6 empty] | 0
52 | [6 empty] | 0
53 | [6 empty] | 0
54 | [6 empty] | 0
55 | [6 empty] | 0
56 | [6 empty] | 0
57 | [6 empty] | 0
58 | [6 empty] | 0
59 | [6 empty] | 0
60 | [6 empty] | 0
61 | [6 empty] | 0
62 | [6 empty] | 0
63 | [6 empty] | 0
64 | [6 empty] | 0
65 | [6 empty] | 0
66 | [6 empty] | 0
67 | [6 empty] | 0
68 | [6 empty] | 0
69 | [6 empty] | 0
70 | [6 empty] | 0
71 | [6 empty] | 0
72 | [6 empty] | 0
73 | [6 empty] | 0
74 | [6 empty] | 0
75 | [6 empty] | 0
76
Always insert blank lines above this row!

## MAYUR
MAYUR's Time Tracking
|  |  | Plan | (hrs) | Actual |  | (hrs)
Row | Date | ActivityID | StartTime | Duration | StartTime | EndTime | Duration | Complete% | Comments
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Always insert blank lines above this row!

## ANUSHA
ANUSHA's Time Tracking
|  |  | Plan | (hrs) | Actual |  | (hrs)
Row | Date | ActivityID | StartTime | Duration | StartTime | EndTime | Duration | Complete% | Comments
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Always insert blank lines above this row!

## JIGEESHA
JIGEESHA's Time Tracking
|  |  | Plan | (hrs) | Actual |  | (hrs)
Row | Date | ActivityID | StartTime | Duration | StartTime | EndTime | Duration | Complete% | Comments
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Always insert blank lines above this row!

## CATHLEEN
CATHLEEN's Time Tracking
|  |  | Plan | (hrs) | Actual |  | (hrs)
Row | Date | ActivityID | StartTime | Duration | StartTime | EndTime | Duration | Complete% | Comments
|  |  | 13:00 | 0.5 |  |  | 0
|  |  | 13:30 | 0.5 |  |  | 0
|  |  | 13:30 | 2 |  |  | 0
|  |  | 12:15 | 0.5 |  |  | 0
|  |  | 13:00 | 0.5 |  |  | 0
|  |  | 13:30 | 0.5 |  |  | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Always insert blank lines above this row!

## CHAITANYA
CHAITANYA's Time Tracking
|  |  | Plan | (hrs) | Actual |  | (hrs)
Row | Date | ActivityID | StartTime | Duration | StartTime | EndTime | Duration | Complete% | Comments
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Always insert blank lines above this row!