## ReadMeFirst
Read Me First - Documentation for this Excel Workbook
| Date | 2022-03-11
| Description | This Excel Workbook holds TrackR TO-BE deliverable list for Picking. Also, the total efforts and time alloted for the various deliverables.
| Author's Team | Team G
| To-Be Sheets Author | Mayurkumar Rafaliya
Below is the list of all the sheets included along with their authors
Code | Tab Name | Full Sheet Name | Authors | Notes
A | ReadMeFirst | This sheet. Gives an overview of the entire workbook
B | To-Be Deliverables | To-Be Deliverables for Assembly
C | Total Efforts | Total efforts and time alloted for various deliverables
Assumptions:

## To-BeDeliverables
ID | Project 2 TO-BE Deliverable | Need /Requirement ID | Start Date | Due Date | Actual Effort Days
1 | Letter of Transmittal | 20 | 2022-03-24 | 2022-03-25 | 1
2 | Cover Page | 20 | 2022-03-24 | 2022-03-25 | 1
3 | Page Headers, Footers and Numbering | 20 | 2022-03-24 | 2022-03-25 | 1
4 | TOC | 20 | 2022-03-24 | 2022-03-25 | 1
5 | Executive Summary | 21 | 2022-03-24 | 2022-03-25 | 1
6 | Assumptions | 21 | 2022-03-24 | 2022-03-25 | 1
7 | Conclusions | 21 | 2022-03-24 | 2022-03-25 | 1
8 | Client Background | 50 | 2022-03-24 | 2022-03-25 | 1
9 | Client vision | 50 | 2022-03-24 | 2022-03-25 | 1
10 | Client Needs | 50 | 2022-03-24 | 2022-03-25 | 1
11 | Client Action | 50 | 2022-03-24 | 2022-03-25 | 1
12 | Client Deliverable | 50 | 2022-03-24 | 2022-03-25 | 1
13 | Requests for Information with NDA (included as an Appendix) | 23 | 2022-03-13 | 2022-03-14 | 1
14 | Project Scope Document | 24 | 2022-03-23 | 2022-03-24 | 1
15 | Detailed References | 23 | 2022-03-24 | 2022-03-25 | 1
16 | Oerview and Rationale | 41 | 2022-03-13 | 2022-03-14 | 1
17 | TO-BE TrackR Production Model | 42 | 2022-03-13 | 2022-03-14 | 1
18 | TO- BE Financial Model | 43 | 2022-03-14 | 2022-03-16 | 2
19 | TO-BE Sunny Day Scenario | 44 | 2022-03-17 | 2022-03-18 | 1
20 | TO-BE Rainy Day Scenario | 44 | 2022-03-18 | 2022-03-19 | 1
21 | TO-BE Factory Layout | 45 | 2022-03-21 | 2022-03-22 | 1
22 | TO-BE Process Flow Diagram | 46 | 2022-03-22 | 2022-03-24 | 2
23 | TO-BE Utilization and Staffing of Labour | 47 | 2022-03-23 | 2022-03-25 | 2
24 | Graphical Analysis of Picking | 49 | 2022-03-23 | 2202-03-24 | 1
25 | Possible Future Analysis and Development, | 26 | 2022-03-23 | 2202-03-24 | 1
26 | Measuring Success and Failure, | 26 | 2022-03-23 | 2202-03-24 | 1
27 | Probable Risks and Benefits of the Suggestions in this Project | 26 | 2022-03-23 | 2202-03-24 | 1
28 | Education/ Training | 48 | 2022-03-16 | 2022-03-17 | 1
29 | Individual Merged Excel Model |  | 2022-03-24 | 2022-03-25 | 1
30 | Individual Merged Report |  | 2022-03-24 | 2022-03-25 | 1
31 | Presentation |  | 2022-03-24 | 2022-03-25 | 1
32 | RACI+, Documentation, Backup Sheets | 25 | 2022-03-16 | 2022-03-25 | 9
33 | Time and Effort Reporting | 25 | 2022-03-16 | 2022-03-25 | 9

## IndividualEffort
RowID | Team Member | Date | TaskID | StartTime | EndTime | Duration | Complete% | Comments
100%
100%
100%
100%
100%
100%
100%
100%

## Reference Sheet
EConestoga. (2022, March 11). INFO8440 Integrated Case Study - P2 Picking To-Be Deliverables 21May07. EConestoga. Retrieved March 11, 2022, https://conestoga.desire2learn.com/d2l/le/content/539481/viewContent/11890101/View